## Sheet1
Name of Center | Africa Centre of Excellence on New Pedagogies in Engineering Education (ACENPEE)
Institution | Ahmadu Bello University, Zaria |  |  | On Schedule
Country | Nigeria
Center Leader | Prof. Raymond B. Bako |  |  | Behind Schedule
Annual Workplan | January - December, 2021
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Centre Management Activities\DLI Action: Centre Management Activities
Sub-Action 1a: Project Annual Planning/Review Retreat
Activity 1: Organize retreat to review and develop Annual Work Plan | Retreat to review and develop 2021 Annual Work Plan | Nil | [12 empty] | Annual Work Plan (AWP) developed |  | 5570 |  |  | Centre Management
Sub-Action 1b: Procurement/Installation of 15kVA Generator
Activity 1: Procurement of 15kVA electricity Generator | Procurement of a15kVA back up power generator | Nil | [12 empty] | 15kVA back power generator procured |  | 15000 |  |  | CD/Procurement officer
Activity 2: Installation of 15kVA electricity Generator | Installation of a15kVA back up power generator | Nil | [12 empty] | 15kVA back power generator installed |  | 2000 |  |  | Centre Management
Sub-Action 1c: ACENPEE Official Project Launch
Activity 1: Organize official project launch | Organize a launch for project visibility and publicity | YES | [12 empty] | ACENPEE officially launched and publicized |  | 5000 |  |  | Communications officer
Activity 2: Production of publicity materials | Produce publicity materials for visibility and publicity | YES | [12 empty] | ACENPEE publicity materials widely circulated |  | 5000 |  |  | Communications officer
Activity 3: Website upgrade and maintenance | To upgrade website and maintenance costs | NIIL | [12 empty] | Website upgraded and maintained |  | 5000
Sub-Action 1d: Capacity Building for Faculty/Administrative staff
Activity 1: Training for 10 Faculty | Sponsorship for 10 Faculty to attend local/international workshops | YES | [12 empty] | 10 Faculty trained |  | 100000 |  |  | Centre Management
Activity 2: Training for 4 Administrative Staff | Sponsorship for 4 Admin. Staff to attend local/international workshops | YES | [12 empty] | 4 Administrative Staff trained |  | 30000 |  |  | Centre Management
Sub-Action 1e: Procurement of Centre Vehicles
Activity 1: Procurement of Sport Utility Vehicle (SUV) | Purchase of Sport Utility Vehicle (SUV) | Nil | [12 empty] | Sport Utility Vehicle Purchased |  | 70000 |  |  | CD/Procurement officer
Activity 2: Procurement of 18 Seater Bus | Purchase of 18 Seater Bus | Nil | [12 empty] | 18 Seater Bus Purchased |  | 50000 |  |  | CD/Procurement officer
Sub-Action 1f: Grant Proposal writing
Activity 1: Organize Meetings for Grant Proposal writing | Meetings to brain storm over grant proposals | YES | [12 empty] | Proposals selected for grant writing |  | 5000 |  |  | Academic/Research Coordinator
Activity 2: Preparation of Grant Proposal documents | Writing and submission of grant proposals for additional funding | YES | [12 empty] | Grant proposals written and submitted |  | 30000 |  |  | Academic/Research Coordinator
Sub - Action Ig: Day to day office management
Activity 1: Payment of wages for office assistants | Payment for driver, cleaners and office assistants | NIL | [12 empty] | Wages of office assistants paid |  | 4000 |  |  | Accountant
Activity 2: Payment for office consumables and utility bills | Payment for office day-to-day consumables | NIL | [12 empty] | Office consumables provided and available for use |  | 23000 |  |  | Procurement officer
Activity 3: Attendance of in-house/out-station meetings | Logistics/refreshment for in-house/out-station meetings | NIL | [12 empty] | Meetings attended in-house/out-station |  | 3000 |  |  | Centre Management
Activity 4: Production of quarterly newsletter | Newsletter to showcase Centre activities | NIL | [12 empty] | Newsletters published |  | 4000 |  |  | Communication officer
Activity 5: Procurement of office furniture/equipment | Provison of office furniture/equipment | NIL | [12 empty] | Office furniture/equipment procured/installed |  | 15000
Activity 6: Reimbursement of expenses already incurred | Payment of loans and services rendered | NIL | [12 empty] | Payment for loans and services achieved |  | 189611
Sub - Action Ih: Attendance of ACE Impact National/Regional Meetings
Activity 1: Travel to attend NPPRC meetings | Members of Centre to attend NPPRC meetings | NIL | [12 empty] | Members attend NPPRC meeting |  | 1000 |  |  | Centre Management
Activity 2: Travel to attend regional meetings | Members of Centre to attend regional meetings | NIL | [12 empty] | Members attend regional workshops |  | 39000 |  |  | Centre Management
Activity 3: Meeting of project stakeholders | Meeting to engage project stakeholders | NIL | [12 empty] | Stakeholders meeting held |  | 2000 |  |  | Centre Management
Action 2: Quantity of Students DLI Action: DLI 3
Sub-Action 2a: Recruitment of Students
Activity 1: Advertisment of Centre programmes | Advertisement of centre programmes in media | NIL | [12 empty] | Centre's Programmes advertised in media |  | 12000 |  |  | Communications officer
Activity 2: Outreach to embassies/regional partners for students | Embassies/regional partners contacted to support student recruitment | YES | [12 empty] | Regional students recruited through Embassies/regional partners |  | 20000 |  |  | Outreach coordinator
Activity 3: Admission processes, screening and registration | Admission processes, screening and registration of students | NIL | [12 empty] | Students admitted, screened and registered |  | 5000 |  |  | Academic/Research Coordinator
Activity 4: Organize professional short courses | Organization of professional short courses | YES | [12 empty] | Professional short courses held |  | 5000 |  |  | Academic/Research Coordinator
Sub-Action 2b: Scholarship to Students
Activity 1: Payment of Tuition fees | Educational and Adminstrative fees | NIL | [12 empty] | Fees and levies paid for students |  | 15000 |  |  | Centre Management
Activity 2: Allowance for Books and School supplies | Books and school materials to be provided to students | NIL | [12 empty] | Books and school materials provided to students |  | 8000 |  |  | Centre Management
Activity 3: Support for Research/Publication | Payment for research consumables and open access publication fees | NIL | [12 empty] | Research and publication support provided |  | 16000 |  |  | Centre Management
Activity 4: Stipend for living expenses | Stipend for living expenses to regional students | NIL | [12 empty] | Stipend for living expenses provided to regional students |  | 11000 |  |  | Centre Management
Sub-Action 2c: Support for Regional Students
Activity 1: Support for Immigration related matters | Consular support to regional students | NIL | [12 empty] | Consular support for students provided |  | 10000 |  |  | Centre Management
Activity 2: Support for English language training | English language training support | NIL | [12 empty] | English language training support provided |  | 4600 |  |  | Centre Management
Sub - Action 2d: Renovation/Furnishing of classrooms and students' hostel
Activity 1: Renovation of physical structure | Renovation of classrooms and student hostels | NIL | [12 empty] | Classrooms and students hostel renovated |  | 12000 |  |  | Centre Management
Activity 2: Furnishing of classrooms and student's hostel | Furnishing for classrooms and student hostels | NIL | [12 empty] | Furnishing for classrooms and students hostels provided |  | 8000 |  |  | Centre Management
Activity 3: Installation of LMS in classrooms | LMS installation in classrooms | NIL | [12 empty] | LMS installed in classrooms (To be provided by NUC) |  | 96477 |  |  | Centre Management
Action 3: Quality of Education\DLI Action: DLI 4
Sub-Action 3a: National/International Accreditation
Activity 1: National Accreditation (NUC Accreditation) | Resource verification and full accreditation | NIL | [12 empty] | Resource verification and accreditation achieved |  | 22000 |  |  | Centre Management
Activity 2: Preparatation for international accreditation (Self evaluation) | Self evaluation for international accreditation | YES | [12 empty] | Self evaluation completed |  | 10000 |  |  | Centre Management
Sub-Action 3b: International Research Publication
Activity 1: Research support and dissemination | Support for research work and dissemination of research findings | NIL | [12 empty] | Research work and result dessimination supported |  | 79500 |  |  | Academic/Research Coordinator
Sub-Action 3c: Milestones for infrastructure improvement
Activity 1: Preparation for centre building | Survey and Subsoil work, Architectural, Structural design, BOQ, M&E and ESMP. | NIL | [12 empty] | Part of DLI 4.3 milestone 1 achieved |  | 55000 |  |  | Centre Management
Action 4: Relevance of Education and Research\DLI 5
Sub-Action 4a: External generated Revenue
Activity 1: Services to organizations | Services to organizations to generate external revenue | NIL | [12 empty] | External revenue generated |  | 5000 |  |  | Accountant
Activity 2: Fund raising through donor and research agencies | Solicitation for prospective donors and collaborators | NIL | [12 empty] | Solicitation done |  | 5000 |  |  | Centre Management
Activity 3: Joint research | Joint research for collaboration to raise funds | YES | [12 empty] | Joint research done and funds raised |  | 7000 | 5000 |  | Academic/Research Coordinator
Sub-Action 4b: Internship
Activity 1: Internship placement | Placement of faculty and students on internship | YES | [12 empty] | Interns placed |  | 11500 | 15000 |  | Academic/Research Coordinator
Sub-Action 4c: Entrepreneurship
Activity 1: Support for entreprenuership start-up | Entrepreneurship start-up from resarch findings | YES | [12 empty] | Startups from research findings initiated |  | 10000 | 10000 |  | Academic/Research Coordinator
Sub-Action 4d: SAB and ISAB Activities
Activity 1: Meetings of Sectoral Advisory Board (SAB) | Meetings for SAB to delibrate on centre activities | NIL | [12 empty] | SAB meetings held |  | 5000 |  |  | Centre Management
Activity 2: Meetings of International Scientific Advisory Board (ISAB) | Meetings for ISAB to delibrate on centre activities | YES | [12 empty] | ISAB meetings held |  | 5000 |  |  | Centre Management
Action 5: Timeliness and Quality of Financial Reports\DLI 6
Sub-Action 5a: Timeliness of Fiduciary Report
Activity 1: Preparation of relevant Financial Reports | Preparation and timely submission of IFRs | NIL | [12 empty] | IFRs submitted timely |  | 5000 |  |  | Accountant
Activity 2: Procurement of Accounting software/training | Procurement of accounting software/training of staff | NIL | [12 empty] | Accounting software procured/staff trained |  | 13000
Sub-Action 5b: Functional Oversight
Activity 1: Establishment of Functional Oversight | Appointment of University Audit Committee | NIL | [12 empty] | University Audit Committee appointed/operational |  | 3000 |  |  | Centre Management
Sub-Action 5c: Web Transparency on Financial Report
Activity 1: Online availiability of Financial Reports | Availability of financial reports on website | NIL | [12 empty] | Financial report available on website |  | 3000 |  |  | Accountant/Communication officer
Sub-Action 5d: Quality of Procurement Planning
Activity 1: Ensuring Quality of Procurement Planning | Quality procurement and planning processes | NIL | [12 empty] | Quality procurement planning achieved |  | 3000 |  |  | Procurement officer
Action 6: Digital Education Network\DLI 7
Sub-Action 6a: ACE thematic network
Activity 1: Planning meetings for network | Planning meetings to kick-start network activities | NIL | [12 empty] | Planning meetings for network take-off held |  | 5000 |  |  | Centre Management
Activity 2: Capacity building | Training to build the capacity of staff for the network | NIL | [12 empty] | Capacity building provided |  | 35000 |  |  | Centre Management
Activity 3:Production and sharing of educational resources | Produce and share educational resources | NIL | [12 empty] | Educational resources produced and shared |  | 10000 |  |  | Academic/Research Coordinator
Sub-Action 6b: Nigerian Researh and Education Network (NgREN)
Activity 1: Subscription to NgREN | Yearly subscription to NgREN | NIL | [12 empty] | NgREN subscribed |  | 50000 |  |  | Centre Management
USD1168258
N443938040
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus