## Disbursement Plan (2)
COUNTRY: NIGERIA
PROJECT: ACE Impact
CENTRE: Africa Centre of Excellence on New Padegogies in Engineering Education
CREDIT NO: IDA
DISBURSEMENT PLAN (JANURY - DECEMBER, 2021)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
| Proposed procurement of 15kVA Power Generator | To power the centre whenever the main source goes off | AMOUNT $: 17000; MONTHS TOTAL: 17000
2 | Proposed production and supply of publicity and circulation materials | To create public awareness on the activities of the centre | AMOUNT $: 5000; MONTHS TOTAL: 5000
3 | Proposed procurement of 18 seater bus | To facilitate and ease project activities. | AMOUNT $: 50000; MONTHS TOTAL: 50000
5 | Proposed production and supply of news letter | To inform and enlighten the students, university community and general public on the activities of the centre | AMOUNT $: 4000; MONTHS TOTAL: 4000
6 | Procurement of office furniture and equipment | To make the staff of the centre perform optimally by furnishing offices with good office furniture and equipment | AMOUNT $: 15000; MONTHS TOTAL: 15000
7 | Furnishing of class rooms and students hostel | To achieve condusive learning environment | AMOUNT $: 8000; MONTHS TOTAL: 8000
8 | Procurement of teaching equipment, materials and books | To enhance students understanding and learning | AMOUNT $: $8,000,00; MONTHS TOTAL: $8,000,00
9 | Supply and installation of learning management system | To enhance students understanding and learning | AMOUNT $: 96477; MONTHS TOTAL: 96000
10 | Procurement of accounting software, installation and training | To ensure best account records keeping and easy retrival of accounting information | AMOUNT $: 13000; MONTHS TOTAL: 13000
11 | Yearly subscription for Nigerian Research and Network (NgREN) | To ensure easy access to Nigeria Research and education network for refrences and other research infoemation | AMOUNT $: 50000; MONTHS TOTAL: 50000
12 | Procurement of a sport utility vehicle (SUV) | For day to day centre logistics. | AMOUNT $: 70000; MONTHS TOTAL: 70000
CONSULTANCIES
| Proposed Acenpee centre building design: Survey and Subsoil work, Architectural, Structural design, BOQ, M&E and ESMP. | Improved Teaching And Research Environment Milestones Formulation | AMOUNT $: 55000
20 | Proposed Upgrade and Maintenance of Website | To give easy access to the ACENPEE's activitie on the centre's web site | AMOUNT $: 5000; MONTHS TOTAL: 5000
NON CONSULTANCY SERVICE
18 | Advertisement of Centre’s Programme In The Media | Proposed Advertisement Of Centre’s Programme In The Media | AMOUNT $: 12000; MONTHS TOTAL: 5000
TRAINING
21 | Confrence and workshops for ACENPEE faculty staff | To train faculty staff in the area of: learning theories, instructional technology and role of media in Engineering education. | AMOUNT $: 100000; MONTHS TOTAL: 100000
22 | Trainings and capacity building for ACENPEE Admin staff | To train admin staff in the area of Administration, Procurement, Accounting and Audit function. | AMOUNT $: 30000; MONTHS TOTAL: 30000
23 | Internship Placement for regional students/staff | To broaden the knowledge of both the students and faculty staff. | AMOUNT $: 11500; MONTHS TOTAL: 11500
24 | Trainings of students from non English speaking countries in English language | To enhance students understanding of English language for easy learning | AMOUNT $: 4600; MONTHS TOTAL: 4600
25 | Meeting of Sectorial Advisory Board (SAB) | To deliberate on centre activities and proffer solutions for the achievement of the centre's mandate. | AMOUNT $: 5000; MONTHS TOTAL: 5000
26 | Meetings of International Scientific Advisory Board (ISAB) | To delibarate on centre's activities and to help expand and deepen partnership and collaborations. | AMOUNT $: 5000; MONTHS TOTAL: 5000
| Organising professional short courses | To organise professional short courses for industry workers and other professionals | AMOUNT $: 5000
OPERATING COST
27 | Payment of wages for assistants | Wages paid to: cleaner, driver, messenger and gardener | AMOUNT $: 4000; MONTHS TOTAL: 4000
28 | Payment for day to day office consumables and utility bills: Cleaning items, maintenance and fuelling of generator, Air time, Internet and refreshments | For efficient running of the affaits of the ACENPEE | AMOUNT $: 23000; MONTHS TOTAL: 23000
29 | Attendance of in-house/out-station meetings | This is to achieve the aim and objectives of ACENPEE | AMOUNT $: 3000; MONTHS TOTAL: 3000
30 | Travellings: Travel to attend NPPRC meetings, Regional meetings and Project stake holders meeting | Thiss is to enable centre management to attend ACE impact National and regional meeting | AMOUNT $: 42000; MONTHS TOTAL: 42000
31 | Recruitment of students | To contact enbassy/regional partners to support student recruitment, admission process, screening and registration | AMOUNT $: 25000; MONTHS TOTAL: 25000
32 | Schorlaship for students: payment of tuition fee, book allowance, school supplies and stipend for living expenses | Educational and Adminstrative fees, Books and school materials to be provided to students Payment for research consumables and open access to publication fees | AMOUNT $: 42000; MONTHS TOTAL: 50000
| Organize official project lounch | Organize for publity and visibilty | AMOUNT $: 5000
| Organize meetings for grant proposal writing | brain storming, writing and submission of grant proposals for additional funding | AMOUNT $: 5000
| Preparation of grant proposal document |  | AMOUNT $: 30000
| Establishment of functional oversight | appointment of the unuversity audit committee | AMOUNT $: 3000
33 | Support for immigration and related matters | Give support to regional student relating to immigration issues | AMOUNT $: 10000; MONTHS TOTAL: 10000
34 | National and International acredition | This is to ensure accredition both nationla and international is achieved | AMOUNT $: 32000; MONTHS TOTAL: 32000
35 | International research publication | To support research and dissemination | AMOUNT $: 79500; MONTHS TOTAL: 79000
36 | External generated revenue | this is to help generate revenue through: services to organisation, donor and research agencies and joint research | AMOUNT $: 17000; MONTHS TOTAL: 17000
37 | Entreprenuership | To support entreprenuership by giving start up capital | AMOUNT $: 10000; MONTHS TOTAL: 10000
38 | Timeliness of fiduciary report | To prepare relevant financial report timely | AMOUNT $: 5000; MONTHS TOTAL: 5000
39 | Web transparency on financial reporting | To ensure availability of finabcial report online | AMOUNT $: 3000; MONTHS TOTAL: 3000
42 | Project annual planning review retreat | To organise retreat on annual work plan | AMOUNT $: 5570; MONTHS TOTAL: 5570
42 | ACE thematic network | To join the degital education network ; planning of meeting for network, capacity and production and sharing of educational resourses | AMOUNT $: $50.000.00; MONTHS MAR: ff; MONTHS TOTAL: 50000
19 | Ensure quality Procurement Planning | To develop good procurement plan for the center | AMOUNT $: 3000; MONTHS TOTAL: 3000
| Reimbursement of expenses already incured | Payment for loan and services achieved | AMOUNT $: 189611; MONTHS TOTAL: 189611
WORKS
| Renovation of classrooms and students hostels | To make the learning environment condusive for students | AMOUNT $: 12000; MONTHS TOTAL: 12000
| = |  | 1168258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159781
|  |  | N443,938,040.00 | [12 empty] | N440,716,780.00

## Procurement plan works
COUNTRY: NIGERIA
PROJECT: ACE Impact
Loan No
NAME OF INSTITUTION: Ahmadu Bello University
WORKS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Substancial Completion | Final Acceptance
[6 empty] | If Prequalification |  | Plan | 2 - 4 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks | NA | 2 to | 4 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
Norm Duration of Proc Steps
GOODS
1 | Proposed renovation of student class room and student hostel | ACENPEE/ABU/21/021 | Lot 19 | $12,000.00 (₦4,560,000.00) | RFQ | Pre Q | Post Review | Plan | 26/1/21 to 16/3/21 | NA | 26/3/21 to 9/4/21 | 9/4/21 to 2/7/21 | 2/7/21 | 2/7/21 to 23/7/21 | 23/7/21 to 2/8/21 | Plan | $12,000.00 (₦4,560,000.00) | 2/8/21 to 9/8/21 | NA | 9/8/21 to 16/8/21 |  | 16/8/21 | 13/9/21
[8 empty] | Actual | [7 empty] | Actual | 0
2 | [16 empty] | 0
| TOTAL AMOUNT |  |  | $12,000.00 (₦4,560,000.00)

## General Work Plan
COUNTRY: NIGERIA
AFRICAN CENTRE OF EXCELLENCE ON NEW PEDAGOGIES IN ENGINEERING EDUCATION
CENTRE NAME WORK PLAN (JANUARY - DECEMBER 2021)
Year 2021
Activity No | ACTIVITY | SUB-ACTIVITY | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT | January - December 2021
[7 empty] | January | February | March | April | May | June | July | August | September | October | November | December
1 | Action 1: Centre Management Activities\DLI Action: Centre Management Activities
Sub-Action 1a: Project Annual Planning/Review Retreat
|  | Activity 1: Organize retreat on annual work plan |  | 5570 |  | Centre Management
Sub-Action 1b: Procurement/Installation of 15kVA Generator
|  | Activity 1: Procurement of 15kVA electricity Generator |  | 15000 |  | CD/Procurement officer
|  | Activity 2: Installation of 15kVA electricity Generator |  | 2000 |  | Centre Management
Sub-Action 1c: ACENPEE Official Project Launch
|  | Activity 1: Organize official project launch |  | 5000 |  | Communications officer
|  | Activity 2: Production of publicity materials |  | 5000 |  | Communications officer
|  | Activity 3: Website upgrade and maintenance |  | 5000
Sub-Action 1d: Capacity Building for Faculty/Administrative staff
|  | Activity 1: Training for 10 Faculty |  | 100000 |  | Centre Management
|  | Activity 2: Training for 4 Administrative Staff |  | 30000 |  | Centre Management
Sub-Action 1e: Procurement of Centre Vehicles
|  | Activity 1: Procurement of Sport Utility Vehicle (SUV) |  | 70000 |  | CD/Procurement officer
|  | Activity 2: Procurement of 18 Seater Bus |  | 50000 |  | CD/Procurement officer
Sub-Action 1f: Grant Proposal writing
|  | Activity 1: Organize Meetings for Grant Proposal writing |  | 5000 |  | Academic/Research Coordinator
|  | Activity 2: Preparation of Grant Proposal documents |  | 30000 |  | Academic/Research Coordinator
Sub - Action Ig: Day to day office management
|  | Activity 1: Payment of wages for office assistants |  | 4000 |  | Accountant
|  | Activity 2: Payment for office consumables and utility bills |  | 23000 |  | Procurement officer
|  | Activity 3: Attendance of in-house/out-station meetings |  | 3000 |  | Centre Management
|  | Activity 4: Production of quarterly newsletter |  | 4000 |  | Communication officer
|  | Activity 5: Procurement of office furniture/equipment |  | 15000
|  | Activity 6: Reimbursement of expenses already incured |  | 189611 |  | Centre Management
Sub - Action Ih: Attendance of ACE Impact National/Regional Meetings
|  | Activity 1: Travel to attend NPPRC meetings |  | 1000 |  | Centre Management
|  | Activity 2: Travel to attend regional meetings |  | 39000 |  | Centre Management
|  | Activity 3: Meeting of project stakeholders |  | 2000 |  | Centre Management
Action 2: Quantity of Students DLI Action: DLI 3
Sub-Action 2a: Recruitment of Students
|  | Advertisement of centre programmes in media |  | 12000 |  | Communications officer
|  | Embassies/regional partners contacted to support student recruitment |  | 20000 |  | Outreach coordinator
|  | Admission processes, screening and registration of students |  | 5000 |  | Academic/Research Coordinator
|  | Organization of professional short courses |  | 5000 |  | Academic/Research Coordinator
Sub-Action 2b: Scholarship to Students
|  | Activity 1: Payment of Tuition fees |  | 15000 |  | Centre Management
|  | Activity 2: Allowance for Books and School supplies |  | 8000 |  | Centre Management
|  | Activity 3: Support for Research/Publication |  | 16000 |  | Centre Management
|  | Activity 4: Stipend for living expenses |  | 11000 |  | Centre Management
Sub-Action 2c: Support for Regional Students
|  | Activity 1: Support for Immigration related matters |  | 10000 |  | Centre Management
|  | Activity 2: Support for English language training |  | 4600 |  | Centre Management
Sub - Action 2d: Renovation/Furnishing of classrooms and students' hostel
|  | Activity 1: Renovation of physical structure |  | 12000 |  | Centre Management
|  | Activity 2: Furnishing of classrooms and student's hostel |  | 8000 |  | Centre Management
|  | Activity 3: Installation of LMS in classrooms |  | 96477 |  | Centre Management
Action 3: Quality of Education\DLI Action: DLI 4
Sub-Action 3a: National/International Accreditation
|  | Activity 1: National Accreditation (NUC Accreditation) |  | 22000 |  | Centre Management
|  | Activity 2: Preparation for international accreditation (Self evaluation) |  | 10000 |  | Centre Management
Sub-Action 3b: International Research Publication
|  | Activity 1: Research support and dissemination |  | 79500 |  | Academic/Research Coordinator
Sub-Action 3c: Milestones for infrastructure improvement
|  | Activity 1: Preparation for centre building |  | 55000 |  | Centre Management
Action 4: Relevance of Education and Research\DLI 5
Sub-Action 4a: External generated Revenue
|  | Activity 1: Services to organizations |  | 5000 |  | Accountant
|  | Activity 2: Fund raising through donor and research agencies |  | 5000 |  | Centre Management
|  | Activity 3: Joint research |  | 7000 |  | Academic/Research Coordinator
Sub-Action 4b: Internship
|  | Activity 1: Internship placement |  | 11500 |  | Academic/Research Coordinator
Sub-Action 4c: Entrepreneurship
|  | Activity 1: Support for entreprenuership start-up |  | 10000 |  | Academic/Research Coordinator
Sub-Action 4d: SAB and ISAB Activities
|  | Activity 1: Meetings of Sectoral Advisory Board (SAB) |  | 5000 |  | Centre Management
|  | Activity 2: Meetings of International Scientific Advisory Board (ISAB) |  | 5000 |  | Centre Management
Action 5: Timeliness and Quality of Financial Reports\DLI 6
Sub-Action 5a: Timeliness of Fiduciary Report
|  | Activity 1: Preparation of relevant Financial Reports |  | 5000 |  | Accountant
|  | Activity 2: Procurement of Accounting software/training |  | 13000
Sub-Action 5b: Functional Oversight
|  | Activity 1: Establishment of Functional Oversight placement |  | 3000 |  | Centre Management
Sub-Action 5c: Web Transparency on Financial Report
|  | Activity 1: Online availiability of Financial Reports |  | 3000 |  | Accountant/Communication officer
Sub-Action 5d: Quality of Procurement Planning
|  | Activity 1: Ensuring Quality of Procurement Planning |  | 3000 |  | Procurement officer
Action 6: Digital Education Network\DLI 7
Sub-Action 6a: ACE thematic network
|  | Activity 1: Planning meetings for network |  | 5000 |  | Centre Management
|  | Activity 2: Capacity building |  | 35000 |  | Centre Management
|  | Activity 3:Production and sharing of educational resources |  | 10000 |  | Academic/Research Coordinator
Sub-Action 6b: Nigerian Researh and Education Network (NgREN)
|  | Activity 1: Subscription to NgREN |  | 50000 |  | Centre Management
| Total |  |  | 1168258
| Operating Expenses 10% |  |  | 116825.8
| Grand Total |  |  | 1285083.8

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: African Centre of Excellence on New Pedagogies in Engineering Education
Loan No
NAME OF INSTITUTION: Ahmadu Bello University, Zaria
PROCUREMENT PLAN FOR GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 2-4weks: | 1.5wk: | 2wks: | 6wks to | 8 wks:3/6/21 | 1.5 - 3 wks | 1 - 1.5 wks: | Plan |  | 1 wk | NA | 1.5-3 wks: | NA | 3wks: | 1wk
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
1 | PROPOSED PROCUREMENT OF 15KVA POWER GENERATOR | ACENPEE/ABU/21/001 | Lot 001 | $17,000.00 (N6,460,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | 17000 |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
2 | PROPOSED PRODUCTION AND SUPPLY OF PUBLICITY CIRCULATION MATERIALS | ACENPEE/ABU/21/002 | Lot 002 | $5,000.00 (N1,900,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | 5000 |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
3 | PROPOSED PROCUREMENT OF 18 SEATER BUS | ACENPEE/ABU/21/003 | Lot 003 | 50000 | R F Q | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | 50000 |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
4 | PROPOSED PROCUREMENT OF OFFICE CONSUMABLES | ACENPEE/ABU/21/004 | Lot 004 | $23,000.00 (N8,740,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $23,000.00 (N8,740,000) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
5 | PROPOSED PRODUCTION AND SUPPLY OF NEWS LETTER | ACENPEE/ABU/21/005 | Lot 005 | $4,000.00 (1,540,000) | R F Q | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $4,000.00 (1,540,000) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
6 | PROCUREMENT OF OFFICE FURNITURE AND EQUIPMENT | ACENPEE/ABU/21/006 | Lot 006 | $15,000.00 (N5,700,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $15,000.00 (N5,700,000) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
7 | FURNISHING OF CLASS ROOMS AND STUDENTS HOSTEL | ACENPEE/ABU/21/007 | Lot 007 | $8,000.00 (N3,404,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $8,000.00 (N3,404,000) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
8 | PROCUREMENT OF TEACHING EQUIPMENT, MATERIALS AND BOOKS | ACENPEE/ABU/21/008 | Lot 008 | $8,000,00 (N3,403,000) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $8,000,00 (N3,403,000) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
9 | SUPPLY AND INSTALLATION OF LEARNING MANAGEMENT SYSTEM | ACENPEE/ABU/21/009 | Lot 009 | $96,000.00 (N36,661,240.00) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $96,000.00 (N36,661,240.00) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
10 | PROCUREMENT OF ACCOUNTING SOFTWARE, INSTALLATION AND TRAINING | ACENPEE/ABU/21/010 | Lot 010 | $13,000.00 (N4,940,000.00) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $13,000.00 (N4,940,000.00) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
11 | YEARLY SUBSCIPTION FOR NIGERIAN RESEARCH AND NETWORK (NGREN) | ACENPEE/ABU/21/011 | Lot 011 | $50,000.00 (N19,000,000.00) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $50,000.00 (N19,000,000.00) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
12 | PROCUREMENT OF A SPORT UTILITY VEHICLE (SUV) | ACENPEE/ABU/21/012 | Lot 012 | $70,000.00 (N26,600,000.00) | RFQ | Pre | Post Review | Plan | 26/1/21 to 16/3/21 | 16/3/21 to 31/3/21 | 31/3/21-8/4/21 | 8/4/21 to | 3/6/21 | 3/6/21-17/6/21 | 17/6/21-28/6/21 | Plan | $70,000.00 (N26,600,000.00) |  |  | 28/6/21-19/7/21 |  | 19/7/21-9/8/21 | 16/8/21
[8 empty] | Actual | [7 empty] | Actual
Actual
|  |  |  | $359,000 (N136,420,000.00) | [12 empty] | $359,000.00 (N136.420,000.00)
TOTAL COST

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO:
NAME AHMADU BELLO UNIVERSITY, ZARIA
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | Centre web site/On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan |  |  | 1 - 2 weeks
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1 | Proposed Acenpee centre building design: Survey and Subsoil work, Architectural, Structural design, BOQ, M&E and ESMP. | QCBS | Lump sum | $55,000.00 (₦20,900,000) | Post Review | Plan | 26/1/21 to 9/3/21 | 9/1/21 to 28/1/21 | 28/1/21 to 10/2/21 | 10/2/21 to 24/2/21 |  | 9/3/21 to 23/3/21 | Plan | 23/3/21 to | 15/6/21 | 15/6/21 to 6/7/21 | 6/7/21 to 20/7/21 | 30/7/21 | 30/7/21 to 13/8/21 | 13/8/21 to 27/8/21 | Plan | 27/8/21 to 10/9/21 | NA |  | 20/9/21 | NA | 20/9/21 to 8/10/21 | Plan | NA |  | 15/10/21 TO 29/10/21 | $55,000.00 (₦20,900,000)
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
| Proposed Upgrade and Maintenance of Website | QCBS | Lump sum | $5,000.00 (N1,900,000.00) | Prior R | Plan | 26/1/21 to 9/3/21 | 9/1/21 to 28/1/21 | 28/1/21 to 10/2/21 | 10/2/21 to 24/2/21 |  | 9/3/21 to 23/3/21 | Plan | 23/3/21 to | 15/6/21 | 15/6/21 to 6/7/21 | 6/7/21 to 20/7/21 | 30/7/21 | 30/7/21 to 13/8/21 | 13/8/21 to 27/8/21 | Plan | 27/8/21 to 10/9/21 |  |  | 20/9/21 |  | 20/9/21 to 8/10/21 | Plan |  |  | 15/10/21 TO 29/10/21 | $5,000.00 (N1,900,000.00)
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
9 | Advertisement of centre programm in the media | QUAL. (Non Consultancy) | Lump sum | $12,000.00 (₦4,560,000.00) | Post Review | Plan | 26/1/21 to 9/3/21 | 9/1/21 to 28/1/21 | 28/1/21 to 10/2/21 | 10/2/21 to 24/2/21 |  | 9/3/21 to 23/3/21 | Plan | 23/3/21 to | 15/6/21 | 15/6/21 to 6/7/21 | 6/7/21 to 20/7/21 | 30/7/21 | 30/7/21 to 13/8/21 | 13/8/21 to 27/8/21 | Plan | 27/8/21 to 10/9/21 |  |  | 20/9/21 |  | 20/9/21 to 8/10/21 | Plan |  |  | 15/10/21 TO 29/10/21 | $12,000.00 (₦4,560,000.00)
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
| TOATAL |  |  | $72,000.00 (N26,460,000.00) | [27 empty] | $72,000.00 (N26,460,000.00)

## Procurement Plan Training
COUNTRY: NIGERIA
PROJECT: ACE - NEW PEDAGOGIES IN ENGINEERING EDUCATION (ACENPEE)
CREDIT NO: IDA
NAME OF INSTITUTION: Ahmadu Bello University
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Confrence and workshops for ACENPEE faculty staff | 10 faculty staff | To train faculty staff in the area of: learning theories, instructional technology and role of media in Engineering education. | Effective teaching and learning that meets international standards. | International/National Institutions | 100000
2 | Trainings and capacity building for ACENPEE Admin staff | 4 admin staff | To train admin staff in the area of Administration, Procurement, Accounting and Audit function. | Efficient centre operations | International/National Institutions | 30000
3 | Internship Placement for regional students/staff | ACE faculty staff/student | To broaden the knowledge of both the students and faculty staff. | Enhanced learning outcomes | International/National Institutions | 11500
4 | Trainings of students from non English speaking countries in English language | MSc/PhD students from Non English speaking countries | To enhance students understanding of English language for easy learning | Proficiency in English language for academic work | Ahmadu Bello University, Zaria | 4600
5 | Meeting of Sectorial Advisory Board (SAB) | Centre management and members of SAB | To deliberate on centre activities and proffer solutions for the achievement of the centre's mandate. | Oversight advisory and supervisory functions of centre activities | Abuja, Nigeria | 5000
6 | Meetings of International Scientific Advisory Board (ISAB) | Centre management and members of ISAB | To delibarate on centre's activities and to help expand and deepen partnership and collaborations. | Oversight advisory and supervisory functions of centre activities | Abuja, Nigeria | 5000
7 | Organising professional short courses | Industry workers and other professionalsS | To organise professional short courses for industry workers and other professionals | Industry workers and other professional to receive training | National | 5000
[5 empty] | TOTAL | 161100
[5 empty] | Naira Equivalent @ N380 to $1 | N61,218,000.00

## Sheet1
17000 | 100000 | 4000
5000 | 30000 | 23000
50000 | 11500 | 3000
$23,000.00 | 4600 | 42000
4000 | 5000 | 25000
15000 | 5000 | 50000
8000 | 5000 | 10000
$8,000,00 | 161100 | 32000
96000 |  | 79500
13000 |  | 17000
50000 |  | 10000
70000 |  | 5000
328000 |  | 3000
35000
5570
50000
3000
189611
586681