## Goods
Country: | NIGERIA
Program: | ACENPEE
Date: | December 2022
Applicable Period: | 2023
Project ID: | P169064
Implementing Agency: | AHMADU BELLO UNIVERSITY | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Estimated Amount Nigeria ₦ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | University notice Board, University Website and Centre Website | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Estimated Amount Nigeria ₦ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Furnishing of students hostel | ACENPEE/ABU/GOODS/001/2023 | LOT 1 | 10000 | 4610000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 10000 | 4610000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Procurement of DLMs for learning and cartridges | ACENPEE/ABU/GOODS/002/2023 | LOT 2 | 40000 | 18440000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 40000 | 18440000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Provide of additional twenty (20) cameras for the LMS facilities in ten (10) classrooms | ACENPEE/ABU/GOODS/003/2023 | LOT 3 | 20000 | 9220000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 20000 | 9220000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Provide 5 inverters with 5 batteries for LMS devices for 10 classrooms | ACENPEE/ABU/GOODS/004/2023 | LOT 4 | 25000 | 11525000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 25000 | 11525000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
[8 empty] | Actual | [7 empty] | Actual
Procure and produce application software such as LabView, animation, etc | ACENPEE/ABU/GOODS/005/2023 | LOT 5 | 50000 | 23050000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 50000 | 23050000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
[8 empty] | Actual | [7 empty] | Actual
Provision of security and safety facilities | ACENPEE/ABU/GOODS/006/2023 | LOT 6 | 5000 | 2305000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 5000 | 2305000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
[8 empty] | Actual | [7 empty] | Actual
Production of publicity materials | ACENPEE/ABU/GOODS/007/2023 | LOT7 | 5000 | 2305000 | RFQ |  |  | Actual | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 5000 | 2305000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Provision of furniture/equipment for the centre | ACENPEE/ABU/GOODS/008/2023 | LOT8 | 10000 | 4610000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 10000 | 4610000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Actual
Provision of solar power system for the Centre | ACENPEE/ABU/GOODS/009/2023 | LOT9 | 10000 | 4610000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 10000 | 4610000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Actual
Provision of laptop/Desktop computers for centre activities | ACENPEE/ABU/GOODS/010/2023 | LOT10 | 15000 | 6915000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 15000 | 6915000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Actual
Purchase of Smart Board and accessories for the Centre Board room | ACENPEE/ABU/GOODS/011/2023 | LOT11 | 10000 | 4610000 | RFQ | N/A | Prior | Plan | 3/4 to 17/4/2023 | 17/4/2023 | 17/4 to 24/4/2023 | N/A | 24/4/2023 | 26/4/2023 | 27/4/2023 | Plan | 10000 | 4610000 | 28/4/2022 | N/A | 30/4/2023 | NA | 14/5/2023 | 17/5/2023
Actual
Total Cost |  |  | 200000 | 92200000 | [12 empty] | 200000 | 92200000
Fill gray cells only!
NOTE 1 USD = 461 NGN AS THE TIME THIS PLAN WAS BEING PREPARED

## Works
Country: | NIGERIA
Program: | ACENPEE
Date: | DECEMBER 2022
Applicable Period: | 2023
Project ID: | P169064
Implementing Agency: | AHMADU BELLO UNIVERSITY | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [9 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Estimated Amount Nigeria ₦ | Pre-Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | 2 NATIONAL DAILIES, FEDERAL TENDER JOURNAL AND CENTER WEB SITE | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Estimated Amount Nigeria ₦ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Estimated Amount in US $ | Estimated Amount Nigeria ₦
Norm Duration of Proc Steps | [6 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks
[7 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
Construction of ACENPEE building complex | ACENPEE/ABU/WORKSS/020/23 | 20 | BOQ | NCB | 300000 | 138300000 | 13/4 TO 18/5/23 | PRIOR | Plan | 22/5/ TO 19/62023 | 26/6/2023 | 26/6-10/7/2022 | 10/7 T0O 17/7/2023 | 24/7/2023 | 21/8/2023 | 28/8/2023 | Plan | 300000 | 138300000 | 1/9/20223 | NA | 6/9/2023 | 6/9/2023 | 6/9/2023 | 6/12/2023 | 300000 | 138300000
Actual
Total Cost |  |  |  |  | 300000 | 138300000 |  |  | Plan | [16 empty] | 300000 | 138300000
Actual
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank
NOTE 1 USD = 461 NGN AS THE TIME THIS PLAN WAS BEING PREPARED

## Consultants 2
Country/Organisation: | NIGERIA
Programme: | ACENPEE
Date: | December 2022
Applicable Period: | 2023
Project ID: | P169064
Implementing Agency: | AHMADU BELLO UNIVERSITY
Request for EOI (where required)
IDA Credit No.: |  |  |  | Contract Type |  |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization | [5 empty] | Contract Implementation |  |  |  |  | Remarks
Description* | Selection Method | Package number | Lot No | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Estimated Amount in ₦ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | CENTER'S WEB AND NOTICE BOARD | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Amount in N₦ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost $ | Final cost ₦
Norm Duration of Proc Steps | [7 empty] | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
Set up an e-library at the centre | LEAST COST | ACENPEE/ABU/CONS./012/2023 | 12 | LUMPSUM | 12000 | 5532000 | PRIOR |  | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 35000 | 16135000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 35000 | 16135000
Subscription to Elsevier/Science Direct Scopus data bases | LEAST COST | ACENPEE/ABU/CONS./013/2023 | 13 | LUMPSUM | 35000 | 16135000 | PRIOR | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 10000 | 4610000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 10000 | 4610000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Subscription to NgREN | LEAST COST | ACENPEE/ABU/CONS./014/2023 | 14 | LUMPSUM | 10000 | 4610000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 5000 | 2303000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 5000 | 2303000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Website upgrade and maintenance | LEAST COST | ACENPEE/ABU/CONS./015/2023 | 15 | LUMPSUM | 5000 | 2303000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 5000 | 2305000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 5000 | 2305000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Provision of enhanced internet connectivity facilties | LEAST COST | ACENPEE/ABU/CONS./016/2023 | 16 | LUMPSUM | 5000 | 2305000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 10000 | 4610000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 10000 | 4610000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Produce a documentary on ACENPEE | LEAST COST | ACENPEE/ABU/CONS./017/2023 | 17 | LUMPSUM | 10000 | 4610000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 39000 | 17979000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 39000 | 17979000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Travels to attend regional meetings | LEAST COST | ACENPEE/ABU/CONS./018/2023 | 18 | LUMPSUM | 39000 | 17979000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 7500 | 3457500 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 7500 | 3457500
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Centre Vehicles insurance | LEAST COST | ACENPEE/ABU/CONS./019/2023 | 19 | LUMPSUM | 7500 | 3457500 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 25000 | 11525000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 25000 | 11525000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Subscription for MIT J-WEL yearly membership | LEAST COST | ACENPEE/ABU/CONS./020/2023 | 20 | LUMPSUM | 25000 | 11525000 |  | Plan | 3/4 to 17/4/2023 | NA | 17/4 to 24/4/2023 | 30/4/2023 | 8/5/2023 | NA |  | 24/5/2023 | 5/6/2023 | 12/6/2023 | 15/6/2023 | 30/6/2023 | 14/7/2023 | 25/7/2023 | PLAN | 27/7/2023 | 31/7/2023 | 12000 | 5532000 | 3/8/2023 | 4/8/2023 | 8/8/2023 | PLAN | 15/8/2023 | 30/8/2023 | 7/9/2023 | 12000 | 5532000
Actual
| TOTAL |  |  |  | 148,500.00 | 68,456,500.00 |  | Plan | [17 empty] | 148,500.00 | 68,456,500.00 | [7 empty] | 148,500.00 | 68,456,500.00
Actual
Plan
| NOTE 1 USD = 461 NGN AS AT THE TIME THIS PLAN WAS BEING PREPARED | [6 empty] | Actual
Plan
Actual
NOTE 1 USD = 461 NGN AS THE TIME THIS PLAN WAS BEING PREPARED