## Sheet1
Name of Centre: | Africa Centre of Excellence on New Pedagogies in Engineering Education (ACENPEE)
Institution: | Ahmadu Bello University, Zaria |  |  | On Schedule
Country: | Nigeria
Centre Leader: | Prof. Raymond B. Bako |  |  | Behind Schedule
Annual Workplan | January - December 2024
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Y4Q1 |  |  | 2024 Y4Q2 |  |  | 2024 Y4Q3 |  |  | 2024 Y4Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible | Estimated Budget($) | Estimated Revenue ($)
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Development Impact DLI 2 | [20 empty] | 5000
Sub-Action 1: Progress Towards Development Impact | [20 empty] | 5000
Activity 1: Completion of SAR and Submission of Documents | Completion of SAR templates and submission of required documents | NIL | [12 empty] | Completed SAR and relevant documents submitted |  | 5000 |  |  | Centre Management | 5000
Action 2: Quantity of Students DLI Action: DLI 3 | [20 empty] | 214000 | 34000
Sub-Action 2a: Sustenance of National and Regional Students (PhD & MSc) | [20 empty] | 18000
Activity 1: Promotion of students programmes | Promotion of students programmes in media | NIL | [12 empty] | Centre students activities promoted |  | 5000 |  |  | Communications Officer | 5000
Activity 2: Outreach to embassies | Embassies contacted to support students consular services | NIL | [12 empty] | Contacts with embassies established to solve students challenges |  | 10000 |  |  | Outreach Coordinator | 10000
Activity 3: Registration processes of students | Screening and registration of students | NIL | [12 empty] | Students admitted, screened and registered |  | 2000 |  |  | Academic Coordinator | 2000
Activity 4: Support to students to complete online verification survey | Guidance and data support for students to complete online verification survey | NIL | [12 empty] | Students guided and supported to complete online survey |  | 1000 |  |  | Academic Coordinator | 1000
Sub-Action 2b: Scholarship for Regional Students (PhD & MSc) | [20 empty] | 40000
Activity 1: Payment of Tuition fees for regional students | Payment of tuition fees and levies for regional students | NIL | [12 empty] | Fees and levies paid for regional students |  | 20000 |  |  | Academic Coordinator | 20000
Activity 2: Allowance for Books and School supplies | Books and school materials to be provided to students | NIL | [12 empty] | Books and school supplies provided to students |  | 2000 |  |  | Academic Coordinator | 2000
Activity 3: Stipend for living expenses for regional students | Stipend for living expenses to regional students | NIL | [12 empty] | Stipend for living expenses provided to regional students |  | 15000 |  |  | Academic Coordinator | 15000
Activity 4: Annual home travel expenses | Provide annual home travel expenses | NIL | [12 empty] | Annual home travel expenses paid for regional students |  | 3000 |  |  | Academic Coordinator | 3000
Sub-Action 2c: In-Country support for Regional Students | [20 empty] | 4000
Activity 1: Support for Immigration related matters | Consular support to regional students | NIL | [12 empty] | Consular support for students provided |  | 2000 |  |  | Academic Coordinator | 2000
Activity 2: Support for English language training | Provide english language training support | NIL | [12 empty] | English language training support provided |  | 2000 |  |  | Academic Coordinator | 2000
Sub-Action 2d: Organize Short Courses, Workshops and Conferences | [20 empty] | 79000 | 34000
Activity 1: Organize professional short courses | Organization of professional short courses | YES | [12 empty] | Professional short courses organized |  | 6000 | 10000 |  | Academic Coordinator | 6000 | 10000
Activity 2: Organize international conference on Engineering Education | An International Conference on Engineering Education to be organised | NIL | [12 empty] | International Conference on Engineering Education Organized |  | 50000 | 20000 |  | Academic Coordinator | 50000 | 20000
Activity 3: Organize workshops for engineering artisans, technicians and technologists on engineering education hardware | Workshops for engineering artisans, technicians and technologist to be organised | NIL | [12 empty] | Workshops for engineering artisans, technicians and technologist organized |  | 5000 | 1000 |  | Academic Coordinator | 5000 | 1000
Activity 4: Organize workshop on sexual harassment and gender violence | Workshops on sexual harassment and gender violence to be organised | NIL | [12 empty] | Workshop on sexual harassment and gender violence organized |  | 5500 | 1000 |  | Gender officer/E&S officer | 5500 | 1000
Activity 5: Organize workshop on course design, delivery and assessment | Workshop on course design delivery and assessment | NIL | [12 empty] | Workshop on course design delivery and assessment organized |  | 7000 | 1000 |  | Academic Coordinator | 7000 | 1000
Activity 6: Organize outreach to secondary schools to promote career choice in Engineering | Outreach to secondary schools to promote career choice in engineering | NIL | [12 empty] | Outreach to secondary school to promote career choice in engineering held |  | 2000 |  |  | Academic Coordinator | 2000
Activity 7: Organize an engineering education fair | To organize an engineering education fair to showcase projects and award of prizes | NIL | [12 empty] | Engineering education fair to showcase engineering projects with award of prizes organized |  | 3500 | 1000 |  | Academic Coordinator | 3500 | 1000
Sub-Action 2e: Certificate in Engineering Education (CEE) Programme | [20 empty] | 22000
Activity 1: CEE course material review | Review of already developed CEE course materials | NIL | [12 empty] | CEE course materials reviewed |  | 5000 |  |  | Academic Coordinator | 5000
Activity 2: CEE programme course delivery | Course delivery of CEE programme by resource persons | NIL | [12 empty] | CEE courses delivered |  | 10000 |  |  | Academic Coordinator | 10000
Activity 3: Assessment of students on CEE programme | Examination and grading of CEE courses | NIL | [12 empty] | Students on CEE programme assessed |  | 3000 |  |  | Academic Coordinator | 3000
Activity 4: Management of CEE programme | Administration of CEE programme | NIL | [12 empty] | CEE programme delivery monitored |  | 4000 |  |  | Academic Coordinator | 4000
Sub - Action 2f: Setting up of e-Library | [20 empty] | 51000
Activity 1: Set up e-libraries at the centre and departments | Provision of furniture, desktop computers, e-materials. | NIL | [12 empty] | e-library established at the temporary centre building and departments |  | 10000 |  |  | ICT officer | 10000
Activity 2: Subscription to education resource data bases | Subscription to education resource data bases | NIL | [12 empty] | Education resource data bases subscribed |  | 10000 |  |  | Academic Coordinator | 10000
Activity 3: Provision of hard and soft library resources at the centre and departments | Hard and soft library resources to participating departments and the centre | NIL | [12 empty] | Hard and Soft library resources to participating departments provided |  | 30000 |  |  | Academic Coordinator | 30000
Activity 4: Purchase of Microsoft 365 software licence | Purchase of Microsoft 365 software licence for the centre | NIL | [12 empty] | Microsoft 365 software licence purchased |  | 1000 |  |  | ICT officer | 1000
Action 3: Quality of Education: DLI 4 | [20 empty] | 1257000
Sub-Action 3a: International Programme Accreditation | [20 empty] | 103000
Activity 1: Implementing recommendations in the self evaluation report from HCERES | Addressing the gaps in the self evaluation report from HCERES | NIL | [12 empty] | Recommendations from the self evaluation report implemented |  | 10000 |  |  | Centre Director | 10000
Activity 2: Accreditation fee to HCERES | Payment of accreditation fee to HCERES | NIL | [12 empty] | Accreditation fees paid to HCERES |  | 35000 |  |  | Centre Director | 35000
Activity 3: Completion of accreditation forms by the departments | Completion of accreditation forms and other logistics for the departments | NIL | [12 empty] | International Programme accreditation forms completed by the departments |  | 2000 |  |  | Centre Director | 2000
Activity 4: Basic facility upgrade towards International accreditation | Upgrade of basic facilities at the centre and in the departments | NIL | [12 empty] | Basic facility upgraded towards international programme accreditation |  | 40000 |  |  | Centre Director | 40000
Activity 5: Collation of accreditation documents by the departments | Collation of accreditation documents by the departments | NIL | [12 empty] | Documents collated for full programme accreditation |  | 2000 |  |  | Academic Coordinator | 2000
Activity 6: Submission of soft and hard accreditation documents to HCERES | Review and submission of soft and hard accreditation documents to HCERES | NIL | [12 empty] | Soft and hard accreditation documents submitted to HCERES |  | 2000 |  |  | Academic Coordinator | 2000
Activity 7: Video recording of centre and departmental facilities for accreditation | Video recording of centre and departmental facilities for accreditation | NIL | [12 empty] | Video recording of centre and departmental facilities carried out |  | 2000 |  |  | Centre Director | 2000
Activity 8: HCERES on-site visit activities | HCERES on-site visit for full accreditation of programmes | NIL | [12 empty] | HCERES on-site visit conducted |  | 10000 |  |  | Centre Director | 10000
Sub-Action 3b: Research and Publication | [20 empty] | 73000
Activity 1: Research support to students | Support for research work to students | NIL | [12 empty] | Students supported to conduct research |  | 15000 |  |  | Research Coordinator | 15000
Activity 2: Research support to faculty | Support for research work to faculty | NIL | [12 empty] | Faculty supported to conduct research |  | 8000 |  |  | Research Coordinator | 8000
Activity 3: Publication support to students and faculty | Support for publication and dissemination of research findings | NIL | [12 empty] | Support to students and faculty for publication and dissemination given |  | 30000 |  |  | Research Coordinator | 30000
Activity 4: Conference attendance support to students and faculty | Support for conference attendance to students and faculty | NIL | [12 empty] | Support to students and faculty for conference attendance given |  | 20000 |  |  | Research Coordinator | 20000
Sub-Action 3c: Milestones for Infrastructure Improvement | [20 empty] | 1081000
Activity 1: Furnishing of students hostel | Furnishing of students hostel | NIL | [12 empty] | Furnishing of students hostels completed |  | 2500 |  |  | Deputy Centre Director | 2500
Activity 2: Installation and training on LMS application | Logistics for LMS installation and training for centre classrooms | NIL | [12 empty] | LMS installed and faculty and students trained |  | 2000 |  |  | Deputy Centre Director | 2000
Activity 3: Procurement of Desktop Learning Modules (DLM) & Cartridges | Procurement of DLMs for teaching and learning | NIL | [12 empty] | Desktop learning modules procured |  | 40000 |  |  | Deputy Centre Director | 40000
Activity 4: Final-payment for consultancy services to ACENPEE building complex | Final payment for Architectural, Structural, M&E, QS services | NIL | [12 empty] | Consultants to ACENPEE building complex final payments made |  | 15000 |  |  | Centre Director | 15000
Activity 5: Residency for consultants on ACENPEE building complex | Provision for residency services of consultants | NIL | [12 empty] | Residency payment made to consultants on ACENPEE building complex |  | 12000 |  |  | Deputy Centre Director | 12000
Activity 6: Contract administration of ACENPEE building complex | Contract administration of ACENPEE building complex | NIL | [12 empty] | ACENPEE building complex properly administered |  | 6000 |  |  | Deputy Centre Director | 6000
Activity 7: Procurement processes for furnishing and equiping the centre building completed | Evaluation to select contractors for furnishing and equiping centre building | NIL | [12 empty] | Procurement processes to select contractors for furnishing completed |  | 5000 |  |  | Centre Management | 5000
Activity 8: Construction of ACENPEE building complex | Construction and finishing of ACENPEE building | NIL | [12 empty] | ACENPEE building constructed to completion level |  | 450000 |  |  | Centre Management | 450000
Activity 9: ESMP activities by the contractor of ACENPEE building complex | Provision for ESMP activities by the contractor of ACENPEE building complex | NIL | [12 empty] | Contractor complied with ESMP guidelines on ACENPEE building complex |  | 10000 |  |  | Safeguard Officer | 10000
Activity 10: Furnishing of ACENPEE building complex | Furnishing of ACENPEE building complex | NIL | [12 empty] | ACENPEE building complex furnished |  | 200000 |  |  | Procurement officer/Centre Director | 200000
Activity 11: Equiping of ACENPEE building laboratories and studios | Equiping of ACENPEE building laboratories and studios | YES | [12 empty] | ACENPEE building laboratories and studios equiped |  | 100000 |  |  | Procurement officer/Centre Director | 100000
Activity 12: Equiping of departmental laboratories and workshops | Equiping of departmental laboratories and workshops | YES | [12 empty] | Departmental laboratories and workshops equiped |  | 160000 |  |  | Procurement officer/Centre Director | 160000
Activity 13: Furnishing of departmental seminar rooms | Furnishing of departmental seminar rooms | NIL | [12 empty] | Departmental seminar rooms furnished |  | 25000 |  |  | Procurement officer/Centre Director | 25000
Activity 14: Provision of cameras for smart boards | Provision of cameras for smart boards in classrooms and seminar rooms | NIL | [12 empty] | Cameras provided for smartboards in classrooms and seminar rooms |  | 2000 |  |  | Centre Management | 2000
Activity 15: Provision of inverters and batteries for classrooms and seminar rooms | Provision of inverters with batteries for LMS devices for classrooms and seminar rooms | NIL | [12 empty] | 5 Inverters with 5 battries for LMS devices for 10 classroom provided |  | 10000 |  |  | Centre Management | 10000
Activity 16: Procure and produce application software such as LabView, animation, etc. | Provision of application software such as Labview, animation, etc | NIL | [12 empty] | Application softwares such as Labview, animation etc, purchased |  | 5000 |  |  | Centre Management | 5000
Activity 17: Provision of power generator and solar power system for ACENPEE building complex | Provision of power generator and solar power system for ACENPEE building complex | NIL | [12 empty] | Power generator and solar power system provided for ACENPEE building complex |  | 20000 |  |  | Centre Management | 20000
Activity 18: Provision of waste collection and disposal facilities for ACENPEE complex | Provision of waste collection and disposal facilities for ACENPEE complex | NIL | [12 empty] | Waste collection and disposal facilities provided for ACENPEE complex |  | 500 |  |  | Centre Management | 500
Activity 19: Beautification of ACENPEE complex | Provision of flowers, paintings, frames, etc, to beautify ACENPEE complex | NIL | [12 empty] | ACENPEE building complex beautified |  | 5000 |  |  | Centre Management | 5000
Activity 20: Modern security gadgets for ACENPEE building complex | Provision for modern security gadgets for ACENPEE building complex | NIL | [12 empty] | Modern security gadgets provided for ACENPEE building complex |  | 5000 |  |  | Centre Management | 5000
Activity 21: Provision of fibre optics internet connectivity to ACENPEE building complex | Provision of fibre optics internet connectivity to ACENPEE building complex | NIL | [12 empty] | Fibre optics internet connectivity provided to ACENPEE building complex |  | 6000 |  |  | Centre Management | 6000
Action 4: Relevance of Education and Research: DLI 5 | [20 empty] | 71000 | 111000
Sub-Action 4a: Externally Generated Revenue | [20 empty] | 21000 | 111000
Activity 1: Consultancy services to organizations | Services to organizations to generate external revenue | YES | [12 empty] | Consultancy services provided to organisations |  | 3000 | 5000 |  | Accountant | 3000 | 5000
Activity 2: Fund raising through donor agencies and philantrophy | Solicitation for prospective donors and philantrophists | YES | [12 empty] | Funds raised from donor agencies and philantrophists |  | 5000 | 20000 |  | Centre Management | 5000 | 20000
Activity 3: Fund raising through research grants | Writing and submission of grant proposals for additional funding | YES | [12 empty] | Funds raised through research grants |  | 5000 | 40000 |  | Centre Management | 5000 | 40000
Activity 4: Joint research activities | Joint research for collaboration to raise funds | YES | [12 empty] | Joint research done and funds raised |  | 4000 | 10000 |  | Research Coordinator | 4000 | 10000
Activity 5: Royalties from patents and innovations, commercialisation of research outcomes | Collection of royalties from patents and innovations, commercialisation of research outcomes | YES | [12 empty] | Arrangement for royalties from patents and innovation completed |  | 2000 | 4000 |  | Research Coordinator | 2000 | 4000
Activity 6: Students' tuition fees | Collection of tuition fees | YES | [12 empty] | Student tuition fees collected |  | 1000 | 30000 |  | Project Accountant | 1000 | 30000
Activity 7: Tender fees | Collection of Tender fees | YES | [12 empty] | Tender fees collected from bidders |  | 1000 | 2000 |  | Procurement officer | 1000 | 2000
Sub-Action 4b: Internship | [20 empty] | 21000 | 0
Activity 1: Internship placement logistics | Sourcing for internship placement opportunities in organisations | NIL | [12 empty] | Internship placement logistics in place |  | 1000 |  |  | Outreach Coordinator | 1000
Activity 2: Internship placement to organizations | Placement of faculty and students on internship in organisations | NIL | [12 empty] | Interns placed in organizations |  | 2000 |  |  | Outreach Coordinator | 2000
Activity 3: Logistic support to students and faculty on internship | Payment of logistic support to students and faculty on internship | NIL | [12 empty] | Internship Logistic support given to students |  | 10000 |  |  | Outreach Coordinator | 10000
Activity 4: Internship supervision | Supervision of faculty and students on internship | NIL | [12 empty] | Internship supervision done |  | 8000 |  |  | Outreach Coordinator | 8000
Sub-Action 4c: Innovation and Entrepreneurship | [20 empty] | 19000 | 0
Activity 1: Develop curriculum for Innovation & entrepreneurship | Development of curriculum for innovation and entrepreneurship | NIL | [12 empty] | Curriculum for Innovation & entrepreneurship developed |  | 3000 |  |  | Partnership Officer | 3000
Activity 2: Host annual innovation week | Organisation of annual innovation week | NIL | [12 empty] | Annual Innovation Week hosted |  | 5000 |  |  | M&E Officer | 5000
Activity 3: Establish faculty consulting business development office | Establishment of faculty consulting business unit | NIL | [12 empty] | Faculty Consulting Business Development Office established |  | 3000 |  |  | Research Coordinator | 3000
Activity 4: Patent research outputs | Patenting of research outputs | NIL | [12 empty] | Research outputs patented |  | 3000 |  |  | Research Coordinator | 3000
Activity 5: Incubation hub and start-ups | Establishment of incubation hub and start-ups | NIL | [12 empty] | Incubation hub and start-ups set up |  | 5000 |  |  | Research Coordinator | 5000
Sub-Action 4d: SAB and ISAB Activities | [20 empty] | 10000
Activity 1: Meetings of Sectoral Advisory Board (SAB) | Meetings for SAB to deliberate on centre activities | NIL | [12 empty] | SAB meetings held |  | 5000 |  |  | Deputy Centre Director | 5000
Activity 2: Meetings of International Scientific Advisory Board (ISAB) | Meetings for ISAB to deliberate on centre activities | NIL | [12 empty] | ISAB meetings held |  | 5000 |  |  | Deputy Centre Director | 5000
Action 5: Timeliness and Quality of Financial Reports: DLI 6 | [20 empty] | 12000
Sub-Action 5a: Timeliness of Fiduciary Report | [20 empty] | 2000
Activity 1: Preparation of relevant Financial Reports | Preparation and timely submission of IFRs | NIL | [12 empty] | IFRs submitted timely |  | 2000 |  |  | Accountant | 2000
Sub-Action 5b: Functional Oversight | [20 empty] | 5000
Activity 1: University Audit Committee activities and report | Submission of University Audit Committee report | NIL | [12 empty] | University Audit Committee report submitted |  | 2000 |  |  | Centre Director | 2000
Activity 2: External Auditing | Payment to External Auditors | NIL | [12 empty] | Externally Audited Account submitted |  | 3000 |  |  | Auditor | 3000
Sub-Action 5c: Web Transparency on Financial Report | [20 empty] | 2000
Activity 1: Upload of Financial Reports to website | Uploading of financial reports on centre website | NIL | [12 empty] | Financial report available on website |  | 2000 |  |  | Communication officer | 2000
Sub-Action 5d: Quality of Procurement Planning | [20 empty] | 3000
Activity 1: Procurement Planning and Processess | Needs assessment & procurement processes | NIL | [12 empty] | Quality procurement planning achieved |  | 2000 |  |  | Procurement officer | 2000
Activity 2: Procurement Audit reports | Submission of procurement audit reports | NIL | [12 empty] | Procurement Audit reports submitted |  | 1000 |  |  | Procurement officer | 1000
Action 6: Institutional Impact: DLI 7 | [20 empty] | 72000
Activity 1: International Institutional accreditation (Gap Assessment) | Gap assessment for international institutional accreditation | NIL | [12 empty] | Gap assessment completed for International Institutional accreditation with QAA |  | 10000 |  |  | Centre Director | 10000
Activity 2: International institutional accreditation (full) | International accreditation of Ahmadu Bello University | NIL | [12 empty] | International Institutional accreditation carried out |  | 50000 |  |  | Centre Director | 50000
Activity 3: Strengthening University research management capacity | Organise capacity building to strengthen University research management capacity | NIL | [12 empty] | University research management capacity strengthened |  | 5000 |  |  | Centre Director | 5000
Activity 4: Strengthening teaching and learning capacity of staff and students | Organise capacity building to strengthen teaching and learning capacity of staff and students | NIL | [12 empty] | Teaching and learning capacity of staff and students strengthened |  | 2000 |  |  | Centre Director | 2000
Activity 5: NgREN verification activities | Hosting of WB mission for NgREN verification | NIL | [12 empty] | NgREN verification exercise carried out |  | 5000 |  |  | Academic Coordinator | 5000
Action 7: Centre Administration | [20 empty] | 312000
Activity 1: Payment of wages for office assistants & drivers | Payment for driver, cleaners and office assistants | NIL | [12 empty] | Wages of office staff paid |  | 4000 |  |  | Accountant | 4000
Activity 2: Recruitment and payment of a project technical assistant | Recruitment of technical assistant to support project implementation | NIL | [12 empty] | Technical assistant employed |  | 5000 |  |  | Centre Management | 5000
Activity 3: Payment for office consumables and utility bills | Payment for office day-to-day consumables and utility bills | NIL | [12 empty] | Office consumables provided and utility bills paid |  | 12000 |  |  | Procurement officer | 12000
Activity 4: Attendance of in-house/out-station meetings | Logistics/refreshment for in-house/out-station meetings | NIL | [12 empty] | Meetings attended in-house/out-station |  | 4000 |  |  | Centre Management | 4000
Activity 5: Production of quarterly newsletter and magazines | Production of newsletters and magazines to showcase Centre activities | NIL | [12 empty] | Newsletters and magazines published |  | 2000 |  |  | Communication officer | 2000
Activity 6: Provision of furniture/equipment for the temporary centre building | Provision of additional furniture/equipment for the temporary centre building | NIL | [12 empty] | Additional furniture and equipment procured for temporary centre building |  | 5000 |  |  | Centre Management | 5000
Activity 7: Provision of solar power system for the temporary centre building | Installation of solar power supply at the temporary centre building | NIL | [12 empty] | Solar power supply provided provided for temporary centre building |  | 8000 |  |  | Centre Management | 8000
Activity 8: Maintenance of temporary centre building and facilities | Routine maintenance of temporary centre building and facilities | NIL | [12 empty] | Temporary office building and facilities maintained |  | 4000 |  |  | Centre Management | 4000
Activity 9: Support to staff for virtual/online activities | Suppport to staff to participate in virtual webinars, workshops, seminars, etc. | NIL | [12 empty] | Support for virtual/online activities provided for staff |  | 5000 |  |  | ICT Officer | 5000
Activity 10: Engagement with project stakeholders | Engagement meetings with relevant project stakeholders | NIL | [12 empty] | Engagement with project stakeholders held |  | 5000 |  |  | Centre Management | 5000
Activity 11: Payment of loans and advances | Payment of loans and advances | NIL | [12 empty] | Loans and advances paid |  | 54000 |  |  | Centre Director | 54000
Activity 12: Travels to attend NPPRC meetings | Members of Centre to attend NPPRC meetings | NIL | [12 empty] | Members attend NPPRC meeting |  | 1000 |  |  | Centre Management | 1000
Activity 13: Travels to attend regional meetings | Members of Centre/VC to attend regional meetings | NIL | [12 empty] | Members/VC attend regional meetings |  | 39000 |  |  | Centre Management | 39000
Activity 14: Fueling and maintenance of Centre vehicles | Fueling and maintenance of Centre vehicles | NIL | [12 empty] | Centre vehicles fueled and maintained |  | 3000 |  |  | Centre Management | 3000
Activity 15: Centre Vehicles insurance | Payment of Centre Vehicles insurance premium | NIL | [12 empty] | Insurance premium of centre vehicles paid |  | 3000 |  |  | Centre Management | 3000
Activity 16: Mission visits to ACENPEE | Mission visits by WB/AAU/NUC teams | NIL | [12 empty] | Mission visits to ACENPEE accomplished |  | 10000 |  |  | Centre Management | 10000
Activity 17: Bi-annual retreats for project review | Retreat to review 2024 project activities | NIL | [12 empty] | Bi-annual retreats for project review undertaken |  | 6000 |  |  | Centre Management | 6000
Activity 18: Retreat to develop 2025 Annual Work Plan | Retreat to develop 2025 Annual Work Plan | NIL | [12 empty] | 2025 Annual Work Plan (AWP) developed |  | 3000 |  |  | Administrative officer | 3000
Activity 19: Production of publicity materials | Produce publicity materials for visibility and publicity | NIL | [12 empty] | ACENPEE publicity materials produced |  | 3000 |  |  | Communications officer | 3000
Activity 20: Website maintenance | Maintenance of ACENPEE website | NIL | [12 empty] | ACENPEE website maintained |  | 2000 |  |  | ICT Officer | 2000
Activity 21: Maintenance of internet facilties | Maintenance of internet facilities at temporary Centre building | NIL | [12 empty] | Internet facilities at temporary centre building maintained |  | 2500 |  |  | ICT Officer | 2500
Activity 22: Production of documentary on ACENPEE | Produce documentary on ACENPEE activities and facilities | NIL | [12 empty] | Documentary on ACENPEE produced |  | 1500 |  |  | Communication officer | 1500
Activity 23: Local and international capacity building for centre faculty | Attendance of local/international workshops/conferences by centre faculty | NIL | [12 empty] | Local and international capacity building for centre faculty achieved |  | 60000 |  |  | Centre Director | 60000
Activity 24: Local and international capacity building for the centre administrative & technical staff | Attendance of local/international workshops by the Centre administrative and technical staff | NIL | [12 empty] | Local and international capacity building for the centre administrative & technical staff achieved |  | 10000 |  |  | Centre Director | 10000
Activity 25: Local and international capacity building for university management | Attendance of local/international workshops/conferences by University management | NIL | [12 empty] | Local and international capacity building for university management achieved |  | 30000 |  |  | Centre Director | 30000
Activity 26: Day-to-day centre administration | Day-to-day running of the centre | NIL | [12 empty] | Centre day-to-day activities administered |  | 10000 |  |  | Centre Director | 10000
Activity 27: Support for African Digital Education Network (ADEN) | Support for African Digital Education Network (ADEN) activities | NIL | [12 empty] | Support given for African Digital Education Network (ADEN) |  | 20000 |  |  | Centre Director | 20000
[21 empty] | 1943000 | 145000
0
Note on V6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus