## Goods
Country: | NIGERIA
Program: | ACENPEE
Date: | December 2023
Applicable Period: | 2024
Project ID: | P169064
Implementing Agency: | AHMADU BELLO UNIVERSITY | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Estimated Amount Nigeria ₦ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Estimated Amount Nigeria ₦ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 1 wks | 2days | 1-3wks | 3wks | 1day | 1.5 wks | 1 - 1.5 days | Plan |  |  | 1 wk |  | 2 wks |  | 2wks | 1wk
[6 empty] | 3-5wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of Hard and Soft library resources to participating departments. | ACENPEE/ABU/GOODS/14/24 | LOT 14 | 30000 | 26820000 | NCB | N/A | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 30000 | 26820000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
Procurement of Desktop Learning Modules (DLM) & Cartridges | ACENPEE/ABU/GOODS/15/24 | LOT 15 | 40000 | 35760000 | NCB | N/A | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 40000 | 35760000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
[8 empty] | Actual | [7 empty] | Actual
Proposed furnishing of new centre building | ACENPEE/ABU/GOODS/16/24 | LOT 16 | 200000 | 178800000 | NCB | 1/2-28/3/24 | Post | Plan | 28/3-5/4-2024 | 7/4/24 | 30/4/24 | 21/5/24 | 21/5/2024 | 29/5/2024 | 31/5/2024 | Plan | 200000 | 178800000 | 7/6/2024 | 7/6/2028 | 21/6-2024 | NA | 5/7/2024 | 12/6/2024
[8 empty] | Actual | [7 empty] | Actual
Proposed Equiping of new ACENPEE building laboratories and studios | ACENPEE/ABU/GOODS/17/24 | LOT 17 | 100000 | 89400000 | NCB | N/A | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 100000 | 89400000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
[8 empty] | Plan | [7 empty] | Actual
Proposed Equiping of departmental laboratories and workshops | ACENPEE/ABU/GOODS/18/24 | LOT 18 | 160000 | 143040000 | NCB | 1/2-28/3/24 | Prior | Plan | 28/3-5/4-2024 | 7/4/24 | 30/4/24 | 21/5/24 | 21/5/2024 | 29/5/2024 | 31/5/2024 | Plan | 160000 | 143040000 | 7/6/2024 | 7/6/2028 | 21/6-2024 | NA | 5/7/2024 | 12/6/2024
[8 empty] | Plan | [7 empty] | Actual
Proposed Furnishing of departmental seminar rooms | ACENPEE/ABU/GOODS/19/24 | LOT 19 | 100000 | 89400000 | NCB | N/A | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 100000 | 89400000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
[8 empty] | Plan | [7 empty] | Actual
Proposed Provision of inverters and batteries for classrooms and seminar rooms | ACENPEE/ABU/GOODS/20/24 | LOT 20 | 35000 | 31290000 | NCB | N/A | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 35000 | 31290000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
[8 empty] | Plan | [7 empty] | Actual
Proposed Procurement of power generator and solar power system for ACENPEE building complex | ACENPEE/ABU/GOODS/21/24 | LOT 21 | 20000 | 17880000 | NCB | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 8/3/24 | 29/3/2024 | 29/3-2024 | 9/4/2024 | 11/4/24 | Plan | 20000 | 17880000 | 18/4/2024 | 18/4/2024 | 1/5/2024 | NA | 15/5-2024 | 22/5/2024
[8 empty] | Plan | [7 empty] | Actual
Provision of furniture/equipment for the directorate of research and innovation of the university | ACENPEE/ABU/GOODS/22/24 | LOT 22 | 35000 | 31290000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 35000 | 31290000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
|  |  |  | 12136750 |  |  |  | actual | [7 empty] | Actual |  | 12136750
Provision of solar power system for the temporary centre building | ACENPEE/ABU/GOODS/23/24 | LOT 23 | 8000 | 7152000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 8000 | 7152000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
[8 empty] | actual | [7 empty] | Actual
Microsoft 365 software licence purchased | ACENPEE/ABU/GOODS/24/24 | LOT 24 | 1000 | 894000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 1000 | 894000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
Furnishing of students hostels completed | ACENPEE/ABU/GOODS/25/24 | LOT 25 | 2500 | 2235000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 2500 | 2235000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
Procure application software such as LabView, animation, etc. | ACENPEE/ABU/GOODS/26/24 | LOT 26 | 5000 | 4470000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 5000 | 4470000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
[8 empty] | Plan | [7 empty] | Actual
Provision of cameras for smart boards | ACENPEE/ABU/GOODS/27/24 | LOT 27 | 2000 | 1788000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 2000 | 1788000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
[8 empty] | Plan | [7 empty] | Actual
Procurement of publicity materials | ACENPEE/ABU/GOODS/28/24 | LOT 28 | 3000 | 2682000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 3000 | 2682000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
[8 empty] | Plan | [7 empty] | Actual
Procurement of quarterly newsletter and magazines | ACENPEE/ABU/GOODS/29/24 | LOT 29 | 2000 | 1788000 | RFQ | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 2000 | 1788000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24
[8 empty] | Plan | [7 empty] | Actual
TOTAL |  |  | 713,500.00 | 637,869,000.00 | [12 empty] | 71,3500.00 | 637,869,000.00
NOTE 1 USD = 894 GN AS THE TIME THIS PLAN WAS BEING PREPARED
NOTE 1 USD = 894 GN AS THE TIME THIS PLAN WAS BEING PREPARED

## Works
Country: | NIGERIA
Program: | ACENPEE
Date: | December 2023
Applicable Period: | 2024
Project ID: | P169064
Implementing Agency: | AHMADU BELLO UNIVERSITY | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
[12 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Estimated Amount Nigeria ₦ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | CENTER WEB AND NOTICE BOARD | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Estimated Amount Nigeria ₦ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Estimated Amount in US $ | Estimated Amount Nigeria ₦
Norm Duration of Proc Steps | [6 empty] | If Prequalification |  | Plan | 1 wks | 2-days | 1-wks | 2-wks | 1day | 2- days | 1- day | Plan |  |  | 1-day |  | 1- day |  | 2wks | 1wk
[7 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
Proposed Basic facility upgrade towards International accreditation | ACENPEE/ABU/WORKS/9/24 | 9 | LUMPSUM | RFQ | 40000 | 35760000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 40000 | 35760000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 40000 | 35760000
[9 empty] | Actual | [7 empty] | Actual
Proposed Provision of waste collection and disposal facilities for ACENPEE complex | ACENPEE/ABU/WORKS/10/24 | 10 | LUMPSUM | RFQ | 500 | 447000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 500 | 447000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 500 | 447000
[9 empty] | Actual | [7 empty] | Actual
Proposed Beautification of ACENPEE complex | ACENPEE/ABU/WORKS/11/24 | 11 | LUMPSUM | RFQ | 5000 | 4470000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 5000 | 4470000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 5000 | 4470000
[9 empty] | Actual | [7 empty] | Actual
Construction of ACENPEE building complex | ACENPEE/ABU/WORKS/12/24 | 12 | LUMPSUM | RFQ | 450000 | 402300000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 450000 | 402300000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 450000 | 402300000
[9 empty] | Actual | [7 empty] | Actual
Maintenance of temporary centre building and facilities | ACENPEE/ABU/WORKS/13/24 | 13 | LUMPSUM | RFQ | 4000 | 3576000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 4000 | 3576000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 4000 | 3576000
[9 empty] | Actual | [7 empty] | Actual
Maintenance of temporary centre building and facilities | ACENPEE/ABU/WORKS/12/24 | 12 | LUMPSUM | RFQ | 4000 | 3576000 | NA | Post | Plan | 1-14/2/24 | 16/2/24 | 23/2/24 | 11/42024 | 11/4/24 | 13/4/24 | 13/4/24 | Plan | 4000 | 3576000 | 14/4/2024 | N/A | 14/4/24 | NA | 28/4/24 | 6/4/24 | 4000 | 3576000
[9 empty] | Actual | [7 empty] | Actual
[5 empty] | 503500 | 450.129,000.00 | [11 empty] | 503500 | 450.129,000.00 | [6 empty] | 503500 | 450.129,000.00
NOTE 1 USD = 894 GN AS THE TIME THIS PLAN WAS BEING PREPARED

## Services
Country/Organisation: |  |  | NIGERIA
Programme: |  |  | ACENPEE
Date: |  |  | December 2023
Applicable Period: |  |  | 2024
Project ID: |  |  | P169064
Implementing Agency: |  |  | AHMADU BELLO UNIVERSITY
Request for EOI (where required)
IDA Credit No.: |  |  |  | Contract Type |  |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization | [5 empty] | Contract Implementation |  |  |  |  | Remarks
Description* | CONTRACT No | Lot Number | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Estimated Amount in N₦ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | CENTER'S WEB AND NOTICE BOARD | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Amount in N₦ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost $ | Final cost ₦
Norm Duration of Proc Steps | [7 empty] | Plan | 1 wk | 1 - 2 wks | 1 - 1.5 wks | 1wk | 1day | 1 - 2 wks | Plan | 2wks | 12 wks | 2 - 3 wks | 1day | 2 wks | 4days | 1wk | Plan | 3days | 1 - 2 wks |  |  | 2days |  | 1WK | Plan |  |  | 2WKS
Component 1:(Instititional Development)
Residency for consultants on ACENPEE building complex (onsultancy service) | ACENPEE/ABU/SVC 1/24 | 1 | IND. CONSL. | LUMPSUM | 12000 | 10728000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | 14-21/2/24 | 21/2/24 | 21/2/24 | Plan | 21/2-7/3/24 | 7/3/24 | 14/3/24 | 14/3/24 | 28/3/24 | 1/4/24 | 8/4/24 | Plan | 11/4/24 | 11/4/24 | 12000 | 10728000 | 13/4/24 | 13/4/24 | 20/4/24 | Plan | NA | NA | 5/5/24 | 12,000 | 10728000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
ACENPEE Website maintenance (Technical services) | ACENPEE/ABU/SVC 2/24 | 2 | RFQ | LUMPSUM | 2000 | 1788000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 2000 | 1788000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 2000.00 | 1788000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Maintenance of internet facilties (Technical services) | ACENPEE/ABU/SVC 3/24 | 3 | RFQ | LUMPSUM | 2500 | 2235000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 2500 | 2235000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 2500 | 2235000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Production of documentary on ACENPEE (Technical services) | ACENPEE/ABU/SVC 4/24 | 4 | RFQ | LUMPSUM | 1500 | 1341000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 1500 | 1341000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 1500 | 1341000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Subscription to education resource data bases | ACENPEE/ABU/SVC 5/24 | 5 | RFQ | LUMPSUM | 10000 | 8940000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 10000 | 8940000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 10000 | 8940000
(Technical services)
Installation and training on LMS application (Technical services) | ACENPEE/ABU/SVC 6/24 | 6 | RFQ | LUMPSUM | 2000 | 1788000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 2000 | 1788000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 2000.00 | 1788000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Set up e-libraries at the centre and departments (Technical services) | ACENPEE/ABU/SVC 7/24 | 7 | RFQ | LUMPSUM | 10,000.00 | 8940000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 10,000.00 | 8940000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 10,000.00 | 8940000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
Proposed Provision of fibre optics internet connectivity to ACENPEE building complex (Technical services) | ACENPEE/ABU/SVC 8/24 | 8 | RFQ | LUMPSUM | 6,000.00 | 5364000 | Post | Plan | 1-7/2/24 | 7/2/24 | 7-14/2/24 | NA | NA | NA | Plan | NA | NA | NA | NA | 14/2/24 | 14/2/24 | NA | Plan | 17/2/24 | 17/2/24 | 6,000.00 | 5364000 | 18/2/24 | NA | 20/2/24 | Plan | NA | NA | 27/2/24 | 6,000.00 | 5364000
[8 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
[5 empty] | 46,000.00 | 41,124,000.00 | [19 empty] | 46,000.00 | 41,124,000.00 | [7 empty] | 46,000.00 | 41,124,000.00
NOTE 1 USD = 894 GN AS THE TIME THIS PLAN WAS BEING PREPARED