## Sheet1
Name of Centre: | Africa Centre of Excellence on New Pedagogies in Engineering Education (ACENPEE)
Institution: | Ahmadu Bello University, Zaria |  |  | On Schedule
Country: | Nigeria
Centre Leader: | Prof. Raymond B. Bako |  |  | Behind Schedule
Annual Workplan | January - June 2025
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y5Q1 |  |  | 2025 Y5Q2 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible | Estimated Budget($) | Estimated Revenue ($)
|  |  | Jan | Feb | Mar | Apr | May | Jun
Action 1: Development Impact: DLI 2 | [14 empty] | 7000
Sub-Action 1: Progress Towards Development Impact | [14 empty] | 7000
Activity 1: Write and produce end of project report | Write and produce a comprehensive end of project report with supporting documents | NIL | [6 empty] | End of project report produced |  | 7000 |  |  | Centre Management | 7000
Action 2: Quantity of Students: DLI 3 | [14 empty] | 267500 | 30500
Sub-Action 2a: Sustenance of National and Regional Students (PhD & MSc) | [14 empty] | 2000
Activity 1: Registration processes of students | Logistics for screening and registration of students | NIL | [6 empty] | Students admitted, screened and registered |  | 2000 |  |  | Academic Coordinator | 2000
Sub-Action 2b: Scholarship for Regional Students (PhD & MSc) | [14 empty] | 145000
Activity 1: Payment of Tuition fees and charges for regional students for remaining period of scholarship | Payment of tuition fees and charges for regional students for remaining period of residency | NIL | [6 empty] | Fees and levies paid for regional students |  | 105000 |  |  | Academic Coordinator | 105000
Activity 2: Allowance for Books and School supplies | Books and school materials to be provided to students | NIL | [6 empty] | Books and school supplies provided to students |  | 20000 |  |  | Academic Coordinator | 20000
Activity 3: Monthly stipend (living expenses) for regional students for the remaining period of scholarship | Monthly stipend for living expenses to regional students for residency | NIL | [6 empty] | Stipend for living expenses provided to regional students |  | 15000 |  |  | Academic Coordinator | 15000
Activity 4: Annual home travel expenses | Provide annual home travel expenses to regional students | NIL | [6 empty] | Annual home travel expenses paid for regional students |  | 5000 |  |  | Academic Coordinator | 5000
Sub-Action 2c: In-Country support for Regional Students | [14 empty] | 4000
Activity 1: Support for Immigration related matters | Provide Consular support to regional students | NIL | [6 empty] | Consular support for students provided |  | 4000 |  |  | Academic Coordinator | 4000
Sub-Action 2d: Organize Short Courses, Workshops and Conferences | [14 empty] | 70500 | 30500
Activity 1: Organize professional short courses | Organization of professional short courses | YES | [6 empty] | Professional short courses organized |  | 6000 | 8000 |  | Academic Coordinator | 6000 | 8000
Activity 2: Organize international conference on Engineering Education | Organize an International Conference on Engineering Education in Africa | NIL | [6 empty] | International Conference on Engineering Education Organized |  | 50000 | 20000 |  | Academic Coordinator | 50000 | 20000
Activity 3: Organize workshops for engineering artisans, technicians and technologists on engineering education hardware | Organize workshops for engineering artisans, technicians and technologists | NIL | [6 empty] | Workshops for engineering artisans, technicians and technologist organized |  | 5000 | 1000 |  | Academic Coordinator | 5000 | 1000
Activity 4: Organize workshop on sexual harassment and gender based violence | Organize workshops on sexual harassment and gender violence to be organised | NIL | [6 empty] | Workshop on sexual harassment and gender violence organized |  | 2500 | 500 |  | Gender officer/E&S officer | 2500 | 500
Activity 5: Organize workshop on course design, delivery and assessment | Workshop on course design delivery and assessment | NIL | [6 empty] | Workshop on course design delivery and assessment organized |  | 5000 | 1000 |  | Academic Coordinator | 5000 | 1000
Activity 6: Organize outreach to secondary schools to promote career choice in Engineering | Outreach to secondary schools to promote career choice in engineering | NIL | [6 empty] | Outreach to secondary school to promote career choice in engineering held |  | 2000 |  |  | Academic Coordinator | 2000
Sub-Action 2e: Certificate in Engineering Education (CEE) Programme | [14 empty] | 10000
Activity 4: Management of CEE programme | Administration of CEE programme | NIL | [6 empty] | CEE programme delivery monitored |  | 10000 |  |  | Academic Coordinator | 10000
Sub - Action 2f: Purchase of Library books and software pakages | [14 empty] | 36000
Activity 1: Purchase of books and library resources for the centre and departments | Hard and soft library resources to participating departments and the centre | NIL | [6 empty] | Hard and Soft library resources to participating departments provided |  | 35000 |  |  | Academic Coordinator | 35000
Activity 2: Purchase of Microsoft 365 software licence | Purchase of Microsoft 365 software licence for the centre | NIL | [6 empty] | Microsoft 365 software licence purchased |  | 1000 |  |  | ICT officer | 1000
Action 3: Quality of Education: DLI 4 | [14 empty] | 640500
Sub-Action 3a: International Programme Accreditation | [14 empty] | 40000
Activity 1: Implement recommendations of the HCERES self evaluation report | Implement the gaps in the self evaluation report from HCERES | NIL | [6 empty] | Recommendations from the self evaluation report implemented |  | 40000 |  |  | Centre Director | 40000
Sub-Action 3b: Research and Publication | [14 empty] | 58000
Activity 1: Payment of research support to students | Payment for research work by students | NIL | [6 empty] | Students supported to conduct research |  | 15000 |  |  | Research Coordinator | 15000
Activity 2: Payment of research support to faculty | Payment for research work by faculty | NIL | [6 empty] | Faculty supported to conduct research |  | 8000 |  |  | Research Coordinator | 8000
Activity 3: Payment for manuscript preparation and publication fees for students and faculty | Payment for manuacript preparation and publication | NIL | [6 empty] | Support to students and faculty for publication and dissemination given |  | 15000 |  |  | Research Coordinator | 15000
Activity 4: Support to attend conferences by students and faculty | Payment for conference attendance to students and faculty | NIL | [6 empty] | Support to students and faculty for conference attendance given |  | 20000 |  |  | Research Coordinator | 20000
Sub-Action 3c: Infrastructure and Learning Environment Improvement | [14 empty] | 542500
Activity 1: Procurement of Desktop Learning Modules (DLM) & Cartridges | Procurement of DLMs for teaching and learning | NIL | [6 empty] | Desktop learning modules procured |  | 40000 |  |  | Deputy Centre Director | 40000
Activity 2: Payment of consultancy fees for ACENPEE building | Payment for Architectural, Structural, M&E, QS services | NIL | [6 empty] | Consultants to ACENPEE building complex final payments made |  | 15000 |  |  | Centre Director | 15000
Activity 3: Contract administration of ACENPEE building complex | Payment for the administration and supervision of ACENPEE building complex | NIL | [6 empty] | ACENPEE building complex properly administered |  | 6000 |  |  | Deputy Centre Director | 6000
Activity 4: Procurement processes for furnishing and equiping the centre building completed | Evaluation to select contractors for furnishing and equiping centre building | NIL | [6 empty] | Procurement processes to select contractors for furnishing completed |  | 5000 |  |  | Centre Management | 5000
Activity 5: Balance payment for the completion of ACENPEE building | Payment for completion and finishing of ACENPEE building | NIL | [6 empty] | ACENPEE building constructed to completion level |  | 50000 |  |  | Centre Management | 50000
Activity 6: Furnishing of ACENPEE building complex | Furnishing of ACENPEE building complex | NIL | [6 empty] | ACENPEE building complex furnished |  | 80000 |  |  | Procurement officer/Centre Director | 80000
Activity 7: Equiping of ACENPEE building laboratories and studios | Equiping of ACENPEE building laboratories and studios | YES | [6 empty] | ACENPEE building laboratories and studios equiped |  | 100000 |  |  | Procurement officer/Centre Director | 100000
Activity 8: Commissioning of ACENPEE building | Commissioning ceremony of completed ACENPEE building | YES | [6 empty] | Departmental laboratories and workshops equiped |  | 10000 |  |  | Procurement officer/Centre Director | 10000
Activity 9: Equiping of departmental laboratories and workshops | Equiping of departmental laboratories and workshops | YES | [6 empty] | Departmental laboratories and workshops equiped |  | 150000 |  |  | Procurement officer/Centre Director | 150000
Activity 10: Furnishing of departmental seminar rooms | Furnishing of departmental seminar rooms | NIL | [6 empty] | Departmental seminar rooms furnished |  | 25000 |  |  | Procurement officer/Centre Director | 25000
Activity 11: Provision of cameras for smart boards | Provision of cameras for smart boards in classrooms and seminar rooms | NIL | [6 empty] | Cameras provided for smartboards in classrooms and seminar rooms |  | 2000 |  |  | Centre Management | 2000
Activity 12: Provision of inverters, solar panels and batteries for departmental classrooms and seminar rooms | Provision of inverters, solar panels and batteries for LMS devices for classrooms and seminar rooms | NIL | [6 empty] | 5 Inverters with 5 battries for LMS devices for 10 classroom provided |  | 15000 |  |  | Centre Management | 15000
Activity 13: Procure application software such as LabView, animation, etc. | Provision of application software such as Labview, animation, etc | NIL | [6 empty] | Application softwares such as Labview, animation etc, purchased |  | 5000 |  |  | Centre Management | 5000
Activity 14: Provision of power generator and solar power system for ACENPEE building complex | Provision of power generator and solar power system for ACENPEE building complex | NIL | [6 empty] | Power generator and solar power system provided for ACENPEE building complex |  | 20000 |  |  | Centre Management | 20000
Activity 15: Provision of waste collection and disposal facilities for ACENPEE complex | Provision of waste collection and disposal facilities for ACENPEE complex | NIL | [6 empty] | Waste collection and disposal facilities provided for ACENPEE complex |  | 500 |  |  | Centre Management | 500
Activity 16: Beautification of ACENPEE complex | Provision of flowers, paintings, frames, etc, to beautify ACENPEE complex | NIL | [6 empty] | ACENPEE building complex beautified |  | 5000 |  |  | Centre Management | 5000
Activity 17: Modern security gadgets for ACENPEE building complex | Provision for modern security gadgets for ACENPEE building complex | NIL | [6 empty] | Modern security gadgets provided for ACENPEE building complex |  | 8000 |  |  | Centre Management | 8000
Activity 18: Provision of fibre optics internet connectivity to ACENPEE building complex | Provision of fibre optics internet connectivity to ACENPEE building complex | NIL | [6 empty] | Fibre optics internet connectivity provided to ACENPEE building complex |  | 6000 |  |  | Centre Management | 6000
Action 4: Relevance of Education and Research: DLI 5 | [14 empty] | 76000 | 110000
Sub-Action 4a: Externally Generated Revenue (Sustainability) | [14 empty] | 23000 | 110000
Activity 1: Consultancy services to organizations | Consultancy services to organizations to generate external revenue | YES | [6 empty] | Consultancy services rendered |  | 4000 | 10000 |  | Centre Management | 4000 | 10000 | 3000 | 10000 | Accountant | 3000 | 10000
Activity 2: Fund raising through donor agencies and philantrophy | Solicitation for prospective donors and philantrophists | YES | [6 empty] | Funds raised from donor agencies and philantrophists |  | 5000 | 20000 |  | Centre Management | 5000 | 20000
Activity 3: Fund raising through research grants | Writing and submission of grant proposals for additional funding | YES | [6 empty] | Funds raised through research grants |  | 5000 | 40000 |  | Research Coordinator | 5000 | 40000
Activity 4: Joint research activities | Joint research for collaboration to raise funds | YES | [6 empty] | Funds raised from joint research |  | 4000 | 15000 |  | Research Coordinator | 4000 | 15000 | 4000 | 10000 | Research Coordinator | 4000 | 10000
Activity 5: Royalties from patents and innovations, commercialisation of research outcomes | Collection of royalties from patents and innovations, commercialisation of research outcomes | YES | [6 empty] | Royalties from patents, innovations and commercialization received |  | 3000 | 10000 |  | Centre Management | 3000 | 10000
Activity 6: Students' tuition fees | Collection of tuition fees | YES | [6 empty] | Students tution fees received |  | 1000 | 10000 |  | Academic Coordinator | 1000 | 10000 | 1000 | 5000 | Project Accountant | 1000 | 5000
Activity 7: Tender fees | Collection of Tender fees | YES | [6 empty] | Tender fees collected |  | 1000 | 5000 |  | Procurement Officer | 1000 | 5000 | 1000 | 5000 | Procurement officer | 1000 | 5000
Sub-Action 4b: Internship | [14 empty] | 21000 | 0
Activity 1: Internship placement logistics | Sourcing for internship placement opportunities in organisations | NIL | [6 empty] | Internship placement logistics in place |  | 1000 |  |  | Outreach Coordinator | 1000
Activity 2: Internship placement to organizations | Placement of faculty and students on internship in organisations | NIL | [6 empty] | Interns placed in organizations |  | 2000 |  |  | Outreach Coordinator | 2000
Activity 3: Logistic support to students and faculty on internship | Payment of logistic support to students and faculty on internship | NIL | [6 empty] | Internship Logistic support given to students |  | 10000 |  |  | Outreach Coordinator | 10000
Activity 4: Internship supervision | Supervision of faculty and students on internship | NIL | [6 empty] | Internship supervision done |  | 8000 |  |  | Outreach Coordinator | 8000
Sub-Action 4c: Innovation and Entrepreneurship | [14 empty] | 22000 | 0
Activity 1: Host annual innovation week and seed grants competition | Organisation of annual innovation week and seed grants competition | NIL | [6 empty] | Annual innovation week and seed grants competetion hosted |  | 10000 |  |  | Research Coordinator | 10000 |  | 25000 |  | M&E Officer | 25000
Activity 2: Patent research outputs | Patenting of research outputs | NIL | [6 empty] | Research outputs patented |  | 5000 |  |  | Research Coordinator | 5000
Activity 3: Furnishing and equiping Incubation hub for start-ups | Establishment of incubation hub and start-ups | NIL | [6 empty] | Incubation hub and start-ups set up |  | 7000 |  |  | Research Coordinator | 7000
Sub-Action 4d: SAB and ISAB Activities | [14 empty] | 10000 | 0
Activity 1: Meeting of Sectoral Advisory Board (SAB) | Meetings for SAB to deliberate on centre activities | NIL | [6 empty] | SAB meetings held |  | 5000 |  |  | Deputy Centre Director | 5000
Activity 2: Meeting of International Scientific Advisory Board (ISAB) | Meetings for ISAB to deliberate on centre activities | NIL | [6 empty] | ISAB meetings held |  | 5000 |  |  | Deputy Centre Director | 5000
Action 5: Timeliness and Quality of Financial Reports: DLI 6 | [14 empty] | 8000
Sub-Action 5a: Timeliness of Fiduciary Report | [14 empty] | 1000
Activity 1: Preparation of project closure financial reports | Preparation and timely submission of IFRs | NIL | [6 empty] | IFRs submitted timely |  | 1000 |  |  | Accountant | 1000
Sub-Action 5b: Functional Oversight | [14 empty] | 3000
Activity 1: External Audit of accounts for project closure | Payment to External Auditors | NIL | [6 empty] | Externally Audited Account submitted |  | 3000 |  |  | Auditor | 3000
Sub-Action 5c: Web Transparency on Financial Report | [14 empty] | 1000
Activity 1: Uploading of Financial Reports to website | Uploading of financial reports on centre website | NIL | [6 empty] | Financial report available on website |  | 1000 |  |  | Communication officer | 1000
Sub-Action 5d: Quality of Procurement Planning | [14 empty] | 3000
Activity 1: Procurement Planning and Processing | Needs assessment & procurement processes | NIL | [6 empty] | Quality procurement planning achieved |  | 1000 |  |  | Procurement officer | 1000
Activity 2: Project closure Procurement Audit reports | End of project procurement audit reports | NIL | [6 empty] | Procurement Audit reports submitted |  | 2000 |  |  | Procurement officer | 2000
Action 6: Institutional Impact: DLI 7 | [14 empty] | 395000
Activity 1: Payment for QAA International institutional accreditation | International accreditation of Ahmadu Bello University | NIL | [6 empty] | International Institutional accreditation carried out |  | 70000 |  |  | Vice Chancellor | 70000
Activity 2: Provision of solar power system for the Senate Building | Provision of solar power system in the Senate building | NIL | [6 empty] | Solar power system provided for Senate building |  | 85000 |  |  | Vice Chancellor | 85000
Activity 3: Furnishing and equiping of Assembly Hall | Furnishing and equiping the Assembly hall for lecture series | NIL | [6 empty] | Assembly hall furnished and equiped |  | 25000 |  |  | Vice Chancellor | 25000
Activity 4: Furnishing and equiping of Vice Chancellors' conference room | Furnishing of the Vice Chancellor's conference room | NIL | [6 empty] | Vice Chancellors office furnished and equiped |  | 20000 |  |  | Vice Chancellor | 20000
Activity 5: Purchase of studio equipment and furniture for Dept of Mass Comm | Provision of studio equipment and furniture in the Dept of Mass Comm | [7 empty] | Studio equipment and furniture provided for mass communication |  | 25000 |  |  | Vice Chancellor | 25000
Activity 6: Purchase and installation of CCTV cameras, digital smart boards and repair of furniture and lights in KIL | Provision of CCTV cameras, digital smart boards, furniture and lighting in KIL | [7 empty] | CCTV cameras, digital smart boards installed and furniture repaired |  | 20000 |  |  | Vice Chancellor | 20000
Activity 7: Furnishing of Virtual Viva Voce rooms in SPGS | Furnishing of Virtual Viva voce rooms in SPGS | [7 empty] | Virtual Viva Voce rooms in SPGS furnished |  | 20000 |  |  | Vice Chancellor | 20000
Activity 8: Procurement of servers and cyber-security applications for Data Centre | Procurement of servers and cyber-security applications for Data Centre | [7 empty] | Servers procured with cyber-security application procured |  | 30000 |  |  | Vice Chancellor | 30000
Activity 9: Procurement of computers and office equipment for Bursary and Registry | Provision of computers and office equipment to Bursary and Registry | [7 empty] | Computers and office equipment procured for Bursary department |  | 20000 |  |  | Vice Chancellor | 20000
Activity 10: Purchase and installation of solar street lights in the campuses | Provision of solar street light in the campuses | [7 empty] | Solar street lights purchased and installed |  | 20000 |  |  | Vice Chancellor | 20000
Activity 11: Provision of boreholes in Kongo campus | Provision of boreholes in Samaru and Kongo campuses | [7 empty] | Boreholes installed in Kongo campus |  | 25000 |  |  | Vice Chancellor | 25000
Activity 12: Landscaping of Engineering phase three premises | Landscape of Engineering phase three premises | [7 empty] | Engineering phase III complex landscaped |  | 20000 |  |  | Vice Chancellor | 20000
Activity 13: Additional furnishing and equipment for Research and Innovation Directorate | [8 empty] | Research and Innovation Directorate furnished |  | 15000 |  |  | Vice Chancellor | 15000
Activity 15: ACENPEE expenses to earn DLI 7 | ACENPEE expenses on DLI 7 recovery | [7 empty] | ACENPEE expenses on DLI 7 recovered |  | 20000 |  |  | Vice Chancellor | 20000
Action 7: Centre Administration | [14 empty] | 284500
Activity 1: Payment of wages for office assistants & drivers | Payment for driver, cleaners and office assistants | NIL | [6 empty] | Wages of office staff paid |  | 4000 |  |  | Accountant | 4000
Activity 2: Payment for office consumables and utility bills | Payment for office day-to-day consumables and utility bills | NIL | [6 empty] | Office consumables provided and utility bills paid |  | 12000 |  |  | Procurement officer | 12000
Activity 3: Attendance of in-house/out-station meetings | Logistics/refreshment for in-house/out-station meetings | NIL | [6 empty] | Meetings attended in-house/out-station |  | 4000 |  |  | Centre Management | 4000
Activity 4: Production of quarterly newsletter and magazines | Production of newsletters and magazines to showcase Centre activities | NIL | [6 empty] | Newsletters and magazines published |  | 2000 |  |  | Communication officer | 2000
Activity 5: Support to staff for virtual/online activities | Suppport to staff to participate in virtual webinars, workshops, seminars, etc. | NIL | [6 empty] | Support for virtual/online activities provided for staff |  | 3000 |  |  | ICT Officer | 3000
Activity 6: Project performance review meeting with project stakeholders | Engagement meetings with relevant project stakeholders | NIL | [6 empty] | Engagement with project stakeholders held |  | 3000 |  |  | Centre Management | 3000
Activity 7: Payment of loans and advances | Payment of loans and advances | NIL | [6 empty] | Loans and advances paid |  | 17000 |  |  | Centre Director | 17000
Activity 8: Travel to attend NPPRC meeting | Members of Centre to attend NPPRC meetings | NIL | [6 empty] | Members attend NPPRC meeting |  | 1000 |  |  | Centre Management | 1000
Activity 9: Travel to attend project closure/10th anniversary meeting | Members of Centre/VC to attend regional meetings | NIL | [6 empty] | Members/VC attend regional meetings |  | 39000 |  |  | Centre Management | 39000
Activity 10: Fueling and maintenance of Centre vehicles | Fueling and maintenance of Centre vehicles | NIL | [6 empty] | Centre vehicles fueled and maintained |  | 3000 |  |  | Centre Management | 3000
Activity 11: Payment of Insurance cover for Centre vehicles | Payment of Centre Vehicles insurance premium | NIL | [6 empty] | Insurance premium of centre vehicles paid |  | 3000 |  |  | Centre Management | 3000
Activity 12: Logistics for mission visits to ACENPEE | Mission visits by WB/AAU/NUC teams | NIL | [6 empty] | Mission visits to ACENPEE accomplished |  | 5000 |  |  | Centre Management | 5000
Activity 13: Production of high quality sourvenirs/publicity materials | Produce publicity materials for visibility and publicity | NIL | [6 empty] | ACENPEE publicity materials produced |  | 10000 |  |  | Communications officer | 10000
Activity 14: Website maintenance | Maintenance of ACENPEE website | NIL | [6 empty] | ACENPEE website maintained |  | 2000 |  |  | ICT Officer | 2000
Activity 15: Production of documentary on ACENPEE | Produce documentary on ACENPEE activities and facilities | NIL | [6 empty] | Documentary on ACENPEE produced |  | 1500 |  |  | Communication officer | 1500
Activity 16: Local and international capacity building | Attendance of local and international workshops by the Centre team and university management | NIL | [6 empty] | Local and international capacity building for centre achieved |  | 145000 |  |  | Centre Director | 145000
Activity 17: Day-to-day centre administration | Day-to-day running of the centre | NIL | [6 empty] | Centre day-to-day activities administered |  | 10000 |  |  | Centre Director | 10000
Activity 18: Support to African Digital Education Network (ADEN) | Support for African Digital Education Network (ADEN) activities | NIL | [6 empty] | Support given for African Digital Education Network (ADEN) |  | 20000 |  |  | Centre Director | 20000
[15 empty] | 1678500 | 140500
Note on N6: Schenineda: If the addition of an activity or component requires further clarification, state it. Expecially since COVID may alter center activities and focus